## Instructions & Master Guide
Executive Master Guide: Digital Twin, BIM & Mega-Construction Infrastructure Dashboard
Architecture Standard | This workbook strictly complies with the Enterprise 14-Sheet Standard and C-Level Reporting Model.
Navigation Protocol | Sheet 2 contains the Executive Hub with 8 primary KPI cards and 2 native distribution charts.
Telemetry Feeds | Operational data from Sheets 3-10 feed summary formulas directly into the Executive Hub.
Target Leadership | Engineered for the Chief Project Director / VP Infrastructure Engineering and executive operations committee.
Audit & Integrity | Pure automated OpenPyXL formulas, active gridlines on every sheet, zero third-party macro dependencies.
Compliance Framework | Cross-walked with ISO, NIST, IEEE, OSHA, and frontier deep-tech industry benchmarks.

## Mega-Project Executive Hub
Digital Twin, BIM & Mega-Construction Infrastructure Dashboard
Executive Control Cockpit ¦ Target Persona: Chief Project Director / VP Infrastructure Engineering ¦ Update Cadence: Real-Time Telemetry
Project Earned Value CPI | Schedule Index SPI | BIM 3D Clash Resolution | IoT Concrete Curing Str | Digital Twin Sync Rate | Lost Time Injuries (LTI) | Contractor Milestone Progress | Total Project Budget Exec
1.04 | 1.02 | 99.4% | 42.8 MPa | 99.8% | 0 Incidents | 94.8% | $1.42B
Cost Performance Index Ahead | Schedule Performance Ahead | Pre-Pour Clashes Cleared | 28-Day Target > 35 MPa | LiDAR Drone Cloud vs CAD | 6.2M Man-Hours Without LTI | On-Track Critical Path | Under Baseline $1.48B
Operational Telemetry Distribution
Subsystem Domain | Telemetry Metric | Score (%)
Main Terminal Tower | Work Completion % | 88
Subway Transit Link | Work Completion % | 82
Runway & Taxiway Slab | Work Completion % | 94
Central Energy Plant | Work Completion % | 91
Baggage Handling Basement | Work Completion % | 86
Critical Readiness Status
Status Tier | Count
Structural Concrete Complete | 45
MEP Engineering In-Progress | 32
Facade & Architectural | 15
Fitout & Commissioning | 8
Executive Priority Watchlist & Remediation Mandates
Watchlist Item | Subsystem | Risk Level | Telemetry Anomaly | Owner | Remediation Action | Target Date | Status
Terminal Roof Truss Node 44 Weld Inspection | Structural Steel | High | Ultrasonic NDT flagged minor void | Lead Structural Inspector | Gouge and reweld node under heat blanket | 2026-10-18 | In Progress
Chilled Water Riser A Pressure Test | MEP HVAC | Low | Hydrostatic test pressure held 16 bar | MEP Resident Engineer | Sign off plumbing hydrostatic clearance | 2026-10-19 | Mitigated
Monthly BIM Clash Resolution & Project Schedule Adherence (%) |  |  |  |  | Digital Twin & Mega Construction BIM Maturity
Month | Target Schedule SPI % | Actual Schedule Adherence % | BIM Clash Resolution Rate % |  | Operational Capability Pillar | Benchmark | Current Attainment
May | 90 | 91.2 | 88 |  | LOD 400 3D Modeling | 4.2 | 4.8
Jun | 91 | 92.5 | 90.4 |  | 4D Time Simulation Sync | 4 | 4.6
Jul | 93 | 94 | 93 |  | 5D Cost EVM Tracking | 4 | 4.5
Aug | 93 | 93.4 | 92.5 |  | IoT Concrete Sensor Mesh | 3.8 | 4.3
Sep | 95 | 96.1 | 95.8 |  | Safety Drone Photogrammetry | 4 | 4.5
Oct | 96 | 97.4 | 98 |  | Subcontractor Quality Gate | 4.2 | 4.7
Daily Construction Concrete Poured (m3) vs BIM Quality Compliance (%) |  |  |  |  | Mega Project Milestone Work Package Execution Status (%)
Day | Concrete Volume (m3) | BIM Spec Compliance % | Target % |  | Work Package | Completed & Signed Off | In-Progress On-Track | Under Quality Inspection | Pending Clashes
Mon | 850 | 96.5 | 95 |  | Foundation Deep Piling | 92 | 5 | 2 | 1
Tue | 920 | 97.2 | 95 |  | Superstructure Core Walls | 68 | 22 | 8 | 2
Wed | 880 | 96.8 | 95 |  | MEP HVAC & Electrical | 45 | 38 | 12 | 5
Thu | 950 | 98.1 | 95 |  | Curtain Wall Facade | 38 | 42 | 14 | 6
Fri | 990 | 98.5 | 97 |  | Interior Fitout & Finishes | 22 | 52 | 18 | 8
Sat | 720 | 99.1 | 97

## BIM 4D Schedule EVM
BIM 4D Schedule EVM
WBS Code | Work Package Name | Budget at Complete ($M) | Planned Value ($M) | Earned Value ($M) | Actual Cost ($M) | CPI | SPI | Status
WBS-101 | Substructure Deep Piling | 84 | 84 | 84 | 81.2 | 1.03 | 1 | Complete
WBS-102 | Superstructure Concrete Core | 165 | 142 | 148 | 141 | 1.05 | 1.04 | Ahead

## Digital Twin LiDAR Point Cloud
Digital Twin LiDAR Point Cloud
Scan Zone | Drone Flight Date | Point Cloud Density | CAD As-Built Deviation (mm) | Tolerance Limit (mm) | Sync Status
Level 14 Floor Slab | 2026-10-14 | 1,200 pts/m² | 3.2 | 10 | Approved Tolerance
Level 15 Steel Columns | 2026-10-14 | 1,450 pts/m² | 4.1 | 12 | Approved Tolerance

## IoT Concrete Curing Sensors
IoT Concrete Curing Sensors
Sensor Tag | Pour Location | Concrete Mix Class | Internal Temp (°C) | Maturity Index (Hours) | Estimated Strength (MPa) | Curing Status
SENS-CONC-01 | Column C-44 Pour | C50/60 High Str | 42.1 | 380 | 48.4 | Full Strength Reached
SENS-CONC-02 | Transfer Slab B | C50/60 High Str | 44.5 | 340 | 44.2 | Full Strength Reached

## MEP 3D Clash Detection
MEP 3D Clash Detection
Clash ID | Trade 1 | Trade 2 | Location Grid | Interference Depth (mm) | Responsible Subcontractor | Resolution State
CLASH-881 | HVAC Duct 800x400 | Fire Sprinkler Main 4" | Grid E-12 Ceiling | 45 | HVAC Subcontractor | Re-routed in BIM 3D
CLASH-882 | Cable Tray 600mm | Sanitary Drain Pipe 6" | Grid F-08 Riser | 30 | Electrical Subcontractor | Resolved Elevation Offset

## Heavy Crane Telematics
Heavy Crane Telematics
Crane ID | Crane Model | Boom Length (m) | Operating Load (t) | Load Moment Indicator (%) | Wind Speed Limit (m/s) | Operator ID
TOWER-CR-01 | Liebherr 550 EC-H | 70 | 12.4 | 62 | 11.2 m/s (Limit 15.0) | CR-OP-101
TOWER-CR-02 | Liebherr 550 EC-H | 70 | 14.1 | 71 | 10.8 m/s (Limit 15.0) | CR-OP-102

## Site HSE Safety Telematics
Site HSE Safety Telematics
Safety Metric | Current Month | YTD Cumulative | Benchmark Standard | HSE Audits Done | Violations Rectified
Lost Time Injury Frequency | 0 | 0 | < 0.50 per 1M hours | 48 | 100% Rectified
Near-Miss Reports Logged | 14 | 82 | Positive Reporting Culture | 48 | 100% Addressed

## Contractor Progress Tracking
Contractor Progress Tracking
Contractor Name | Scope of Work | Contract Value ($M) | Certified Progress (%) | Invoiced Amount ($M) | Retainage Held ($M) | Quality Rating
MegaSteel Corp | Structural Steel Erection | 142 | 89.4 | 126.9 | 6.3 | Grade A
Global MEP Joint Venture | Mechanical Electrical Plumbing | 185 | 78.2 | 144.6 | 7.2 | Grade A

## Geotechnical Inclinometer
Geotechnical Inclinometer
Borehole ID | Location | Inclinometer Depth (m) | Cumulative Lateral Deflection (mm) | Piezometer Water Table (m) | Ground Settlement Status
INC-BH-01 | Excavation Pit North Wall | 35 | 4.2 | -6.4 | Stable Within Tolerance
INC-BH-02 | Excavation Pit South Wall | 35 | 3.8 | -6.2 | Stable Within Tolerance

## Sustainability LEED Gold
Sustainability LEED Gold
LEED Credit Category | Target Points | Earned Points | Material Recycled Content (%) | Construction Waste Diverted (%) | Rating Tier
Materials & Resources | 14 | 13 | 32.4% Recycled Aggregates | 94.2% Diverted From Landfill | LEED Gold Certified Track

## Site Non-Conformance (NCR)
Site Non-Conformance (NCR)
NCR Number | Location | Non-Conformance Description | Defect Class | Disposition Action | Sign-Off Engineer
NCR-2026-44 | Level 12 Slab Pour | Surface honeycombing on shear wall edge | Cosmetic Minor | Pressure epoxy injection repair | Resident Engineer PE

## Mega-Project Cash Flow FinOps
Mega-Project Cash Flow FinOps
Month Window | Projected Cash Outflow ($M) | Actual Billed ($M) | Variance ($M) | Escrow Facility Balance | Contingency Drawdown
October 2026 | 42 | 40.8 | -1.2 | $180M Available | Zero Drawdown

## Engineering Change Order (ECO)
Engineering Change Order (ECO)
ECO Code | Discipline | Scope Modification | Cost Impact ($) | Schedule Impact (Days) | Client Approval Status
ECO-BIM-112 | Architectural Facade | Upgraded glass thermal double glazing | 140000 | 0 | Approved by Client