## Instructions
🏛️ ENTERPRISE ARCHITECTURE (EA) & LEGACY MODERNIZATION DASHBOARD
Application Portfolio Management (APM), Gartner TIME model, tech stack lifecycle, and cloud migration governance.
NO | SHEET NAME | DOMAIN / MODULE | KEY METRICS TRACKED | FORMULA AUTOMATION LEVEL
1 | Executive EA Dashboard | Executive Architecture Command | Application Portfolio, TIME Model Split, Tech Debt Drag, Cloud % | 100% Dynamic Formula Driven
2 | Application Portfolio (APM) | Enterprise Application Inventory | Business Value vs Technical Fit, Annual Run Cost, TIME Strategy | Formula Driven Recommendations
3 | TIME Framework Analysis | Gartner TIME Categorization | Tolerate, Invest, Migrate, Eliminate Run Costs ($) and Roadmaps | Financial Aggregations
4 | Tech Stack & EOL Lifecycle | Technology Component Obsolescence | Framework EOL Dates, Days to Deprecation, Upgrade Complexity | Automated EOL Warning Flags
5 | Architecture Review (ARB) | ARB Governance & Submissions | Solution Blueprints, Review Decisions, Architectural Debt Conditions | Approval RAG Tracking
6 | API & Integration Matrix | System Integration Topology | REST, gRPC, Event Brokers, Reusability Scores, Data Sensitivity | Reusability Index
7 | Cloud Migration (6Rs) | Cloud Modernization Strategy | Rehost, Replatform, Refactor, Repurchase, Retain, Retire Progress | Migration Completion %
8 | Technical Debt Valuation | Architectural Debt Financials | Estimated Remediation Effort (Days), Financial Drag Cost ($) | Debt Cost Summation
9 | Microservices & Monoliths | Service Decomposition Health | Database per Service Compliance, Domain Decoupling Progress | Decoupling Metrics
10 | Data Architecture Topology | Data Mesh & Golden Sources | System of Record (SoR), CDC Ingestion Latency, Domain Ownership | Data Governance Status
11 | Inter-System Dependencies | Failure Blast Radius Analysis | Upstream vs Downstream Coupling, Circuit Breaker Resilience | Blast Radius Scoring
12 | EA Standards & Guardrails | Architecture Policy Compliance | Containerization, Observability, Linter Compliance Violations | Compliance % Rates
13 | Strategic EA Scorecard | Enterprise Architecture Maturity | Standards Adoption, Modernization Velocity, Cloud-Native Footprint | Weighted Index Formula

## Executive EA Dashboard
🏛️ ENTERPRISE ARCHITECTURE (EA) & MODERNIZATION EXECUTIVE DASHBOARD
Real-time enterprise application portfolio health, TIME model allocation, tech debt valuation, and cloud modernization.
TOTAL ENTERPRISE APPS |  |  | TOTAL ANNUAL RUN COST |  |  | APPS TO MODERNIZE (TIME) |  |  | CLOUD-NATIVE ADOPTION %
ANNUAL TECH DEBT DRAG ($) |  |  | ACTIVE TECH EOL ALERTS |  |  | ARB APPROVED BLUEPRINTS % |  |  | API REUSABILITY INDEX
APPLICATION COUNT BY GARTNER TIME MODEL | [5 empty] | CLOUD MIGRATION 6R STRATEGY BREAKDOWN
TIME Category | App Count |  |  |  |  | 6R Strategy | Workloads
Invest (Strategic) | [5 empty] | Refactor (Cloud-Native)
Tolerate (Stable) | [5 empty] | Replatform (PaaS/Managed)
Migrate (Modernize) | [5 empty] | Rehost (Lift & Shift)
Eliminate (Decommission) | [5 empty] | Repurchase (SaaS)
TOP CRITICAL LEGACY MODERNIZATION TARGETS
APP ID | APPLICATION NAME | BUSINESS VALUE | TECHNICAL QUALITY | TIME ACTION | ANNUAL RUN COST ($) | TARGET ARCHITECTURE | RAG STATUS
APP-01 | Core Banking Mainframe Ledger | High | Low | Migrate | 1250000 | Cloud-Native Microservices | At Risk
APP-02 | Legacy Customer Billing POS | Medium | Low | Eliminate | 420000 | SaaS Replacement (Stripe) | Optimal
APP-03 | Enterprise Data Warehouse (On-Prem) | High | Low | Migrate | 680000 | Snowflake / BigQuery Lakehouse | At Risk
APP-04 | Mobile Banking App v3.2 | High | Medium | Invest | 350000 | Modern Flutter Micro-frontends | Optimal
| Monthly Cloud Migration Velocity & Legacy Tech Debt Reduction (%) |  |  |  |  | Enterprise Architecture (TOGAF) Modernization Index
| Month | Target Migration % | Actual Workloads Migrated % | Tech Debt Reduction Index % |  | Operational Capability Pillar | Benchmark | Current Attainment
| May | 60 | 62.5 | 45 |  | Domain-Driven Microservices | 4 | 4.6
| Jun | 65 | 67.8 | 49.5 |  | Mainframe Cloud Offload | 3.8 | 4.3
| Jul | 70 | 73.2 | 54 |  | Event-Driven Kafka Mesh | 4.2 | 4.7
| Aug | 70 | 72.8 | 53.5 |  | API-First Standardization | 4.2 | 4.8
| Sep | 75 | 78.4 | 59 |  | Architectural Fitness Functions | 3.8 | 4.4
| Oct | 80 | 84.1 | 65 |  | Multi-Cloud Vendor Portability | 4 | 4.5
| Enterprise Application Portfolio Modernization Profile |  |  |  |  | System Technical Debt (k USD) vs Business Criticality Tier
| Month | Cloud Native Microservices | Re-platformed Containers | Encapsulated APIs | Legacy Monoliths | Core Domain | Tech Debt ($k) | Criticality (1-10) | Annual OpEx ($k)
| May | 120 | 85 | 65 | 180 | Core Billing Engine | 450 | 9.8 | 1200
| Jun | 138 | 96 | 72 | 164 | Customer Portal | 180 | 8.5 | 480
| Jul | 162 | 110 | 80 | 148 | Inventory Manager | 320 | 8.9 | 850
| Aug | 160 | 108 | 78 | 144 | Internal HR Hub | 85 | 4.5 | 180
| Sep | 188 | 124 | 88 | 120 | Supplier Extranet | 210 | 6.8 | 520
| Oct | 220 | 142 | 95 | 93 | Warehouse Dispatch | 290 | 8.2 | 740

## Application Portfolio (APM)
📋 APPLICATION PORTFOLIO MANAGEMENT (APM) & TECHNICAL FIT LEDGER
| Total Applications: |  |  | Total Run Spend ($):
APP ID | APPLICATION NAME | BUSINESS CAPABILITY | BUSINESS VALUE | TECHNICAL QUALITY | TIME STRATEGY | HOSTING MODEL | ANNUAL RUN COST ($) | BUSINESS OWNER | TECH OWNER | LIFECYCLE
APP-01 | Core Banking Mainframe | Core Deposits & Ledger | High | Low | Migrate | On-Premises Mainframe | 1250000 | VP Retail Banking | Lead Architect | Legacy Active
APP-02 | Legacy POS Terminal Engine | Merchant Storefront | Medium | Low | Eliminate | On-Premises Dedicated | 420000 | Head of Merchant Ops | Infra Lead | Phase Out
APP-03 | Enterprise Data Warehouse | BI & Regulatory Reporting | High | Low | Migrate | On-Premises Appliance | 680000 | Chief Data Officer | Data Architect | Migrating
APP-04 | Mobile Banking App v3.2 | Customer Mobile Channels | High | Medium | Invest | AWS Cloud-Native | 350000 | VP Digital | Mobile Pod Lead | Active Growth
APP-05 | Customer Support CRM | Support Ticket Desk | High | High | Tolerate | Salesforce SaaS | 480000 | VP Customer Support | SaaS Admin | Active
APP-06 | Corporate Human Resources | Payroll & Employee Ledger | Medium | High | Tolerate | Workday SaaS | 320000 | HR Director | Enterprise Architect | Active
APP-07 | Inventory Logistics Sync | Warehouse Stock Movement | Medium | Medium | Tolerate | Hybrid Azure VM | 290000 | VP Supply Chain | Solution Architect | Active
APP-08 | Fraud AI Detection Engine | Risk & Transaction Defense | High | High | Invest | GCP Cloud-Native AI | 540000 | Chief Risk Officer | AI Architect | Active Growth

## TIME Framework Analysis
🧭 GARTNER TIME MODEL STRATEGIC ROADMAP & PORTFOLIO ALLOCATION
TIME CATEGORY | BUSINESS FIT | TECHNICAL FIT | TOTAL APPS | ANNUAL SPEND ($) | STRATEGIC RATIONALE | ACTION PLAN | HEALTH STATUS
Invest | High Business Value | High Tech Quality |  |  | Modernize features, scale cloud infrastructure, accelerate roadmap | Inject engineering pods & enhance capabilities | Optimal
Tolerate | Medium-High Value | Acceptable Quality |  |  | Stable utility systems; maintain without significant changes | Keep operational with minimal maintenance spend | Optimal
Migrate | High Business Value | Low Tech Quality |  |  | Critical functionality trapped in obsolete legacy code | Replatform to cloud-native microservices architecture | At Risk
Eliminate | Low Business Value | Low Tech Quality |  |  | Redundant shelfware, obsolete point solutions, technical debt | Decommission, archive data, and cancel licenses | Action Required

## Tech Stack & EOL Lifecycle
⚠️ TECHNOLOGY STACK LIFECYCLE & END-OF-LIFE (EOL) TRACKER
TECH ID | COMPONENT / LANGUAGE | CURRENT VERSION | VENDOR EOL DATE | DAYS TO EOL | TARGET UPGRADE VERSION | MIGRATION RISK | ASSIGNED ARCHITECT | STATUS
TECH-01 | Java Runtime Environment | Java 8 (Oracle) | 2026-12-31 |  | OpenJDK 21 LTS | High | Bambang Wijaya | Action Required
TECH-02 | Python Data Pipeline | Python 3.8 | 2024-10-31 | -715 | Python 3.12 | Critical | Rian Hidayat | EOL Breached
TECH-03 | Node.js Microservices | Node 18 LTS | 2025-04-30 | -533 | Node 22 LTS | Medium | Alex Chen | Upgrading
TECH-04 | PostgreSQL Database Tier | PostgreSQL 12 | 2024-11-14 | -701 | PostgreSQL 16 | High | Siti Rahma | EOL Breached
TECH-05 | Kubernetes Fleet | K8s v1.27 | 2024-06-28 | -840 | K8s v1.30 | Medium | DevOps Guild | Upgrading

## Architecture Review (ARB)
🏛️ ARCHITECTURE REVIEW BOARD (ARB) GOVERNANCE & BLUEPRINTS
ARB ID | SUBMISSION TITLE | REQUESTING SQUAD | ARCHITECTURAL PATTERN | TARGET CLOUD | REVIEW DATE | ARB DECISION | CONDITIONS / ACTION ITEMS | STATUS
ARB-201 | Real-Time Event Ingestion Engine | Data Platform Pod | Event-Driven (Kafka) | GCP GKE | 2026-09-15 | Approved | Must implement schema registry validation | Approved
ARB-202 | Mobile BFF Microservices Gateway | Mobile Guild | GraphQL & REST Gateway | AWS EKS | 2026-09-22 | Approved | Enforce rate limiting & WAF rules | Approved
ARB-203 | Legacy Monolith Direct DB Query | BI Analytics | Shared Database Anti-Pattern | On-Prem | 2026-10-05 | Rejected | Violates decoupling standard; use Kafka CDC | Rejected

## API & Integration Matrix
🔌 ENTERPRISE API CATALOG & SYSTEM INTEGRATION TOPOLOGY
INTEGRATION ID | SOURCE SYSTEM | TARGET SYSTEM | PROTOCOL / TRANSPORT | SYNC / ASYNC | REUSABILITY SCORE (1-5) | DATA CLASSIFICATION | THROUGHPUT (RPS) | STATUS
INT-01 | Mobile Banking App | Payment Gateway API | REST / JSON (mTLS) | Synchronous | 4.8 | Confidential PII | 450 | Optimal
INT-02 | Core Banking Ledger | Enterprise Lakehouse | Kafka CDC Streaming | Asynchronous | 5 | Confidential Financial | 1200 | Optimal
INT-03 | Legacy POS Terminal | Mainframe Batch Settlement | SFTP File Transfer | Batch Async | 1.5 | Financial Records | 15 | At Risk
INT-04 | Customer Support CRM | Notification Engine | Webhook Event Push | Asynchronous | 4.2 | Customer PII | 180 | Optimal

## Cloud Migration (6Rs)
☁️ CLOUD MIGRATION STRATEGY & 6R MODERNIZATION WAVES
WORKLOAD ID | WORKLOAD / SERVICE NAME | 6R STRATEGY | MIGRATION WAVE | TARGET ARCHITECTURE | EST. EFFORT (MONTHS) | COMPLETION % | CUTOVER DATE | STATUS
WKL-01 | Core Banking Transactions | Refactor | Wave 3 | Microservices on AWS EKS | 18 | 72% | 2026-12-15 | In Progress
WKL-02 | Customer Data Marts | Replatform | Wave 2 | Google Cloud BigQuery | 8 | 88% | 2026-11-20 | In Progress
WKL-03 | Legacy Billing Appliance | Repurchase | Wave 1 | Stripe Enterprise SaaS | 6 | 100% | 2026-08-30 | Completed
WKL-04 | Internal Intranet Portal | Rehost | Wave 1 | Azure VM Lift & Shift | 3 | 100% | 2026-07-15 | Completed

## Technical Debt Valuation
💸 ARCHITECTURAL & TECHNICAL DEBT FINANCIAL VALUATION
DEBT ID | SYSTEM / REPO | TECHNICAL DEBT DESCRIPTION | REMEDIATION EFFORT (DAYS) | ANNUAL FINANCIAL DRAG ($) | PAYOFF URGENCY | PROPOSED SOLUTION | STATUS
TDB-01 | Core Banking Mainframe | Hardcoded COBOL batch scripts lack automated unit tests | 120 | 450000 | High | Decompose into Go microservices with test fixtures | In Progress
TDB-02 | Legacy POS Terminal | Direct point-to-point SQL queries cause database lockups | 45 | 180000 | High | Deploy API caching layer with Redis | Approved
TDB-03 | Mobile Banking App | Monolithic frontend state management spaghetti code | 30 | 95000 | Medium | Migrate to BLoC architectural state pattern | In Progress
TDB-04 | Reporting DB | Unindexed large tables causing CPU 95% spikes | 15 | 65000 | Medium | Partition tables & rebuild b-tree indexes | Approved

## Microservices & Monoliths
🧩 SERVICE DECOMPOSITION & DOMAIN BOUNDARY TOPOLOGY
DOMAIN ID | BUSINESS DOMAIN | ARCHITECTURE STYLE | TOTAL SERVICES | DATABASE PER SERVICE | OBSERVABILITY SCORE % | DECOUPLING STATUS | HEALTH
DOM-01 | Checkout & Payments | Cloud Microservices | 12 | Yes (Postgres/Redis) | 95% | Fully Decoupled | Optimal
DOM-02 | Customer Identity & Auth | Modular Microservices | 6 | Yes (Azure SQL) | 92% | Fully Decoupled | Optimal
DOM-03 | Order Fulfillment & Stock | Semi-Decoupled Monolith | 4 | No (Shared Schema) | 74% | Decomposing | At Risk
DOM-04 | General Ledger Accounting | Legacy Monolith | 1 | No (Monolithic DB) | 60% | Tightly Coupled | At Risk

## Data Architecture Topology
🗄️ ENTERPRISE DATA ARCHITECTURE, GOLDEN RECORDS & DATA MESH
DATA DOMAIN | SYSTEM OF RECORD (SOR) | STORAGE TECH | INGESTION LATENCY | GOLDEN RECORD SCHEMA | DATA MESH PRODUCT OWNER | DATA QUALITY INDEX | STATUS
Customer 360 | Identity Okta & CRM | Snowflake Gold Layer | < 15 Mins | Standardized JSON Schema | Customer Data Steward | 98.5% | Optimal
Financial Transaction Ledger | Core Banking Postgres | Iceberg Lakehouse Table | Real-Time CDC | Strict ACID Avro Schema | Finance Data Lead | 99.9% | Optimal
Product Catalog Master | Cloud Spanner Catalog | Redis & BigQuery | < 1 Min | GraphQL Schema Entity | Merchant Catalog Lead | 97% | Optimal

## Inter-System Dependencies
🕸️ INTER-SYSTEM DEPENDENCY GRAPH & BLAST RADIUS MATRIX
DEP ID | UPSTREAM CALLER | DOWNSTREAM SERVICE | COUPLING TYPE | FAILURE BLAST RADIUS | CIRCUIT BREAKER INSTALLED | FALLBACK STRATEGY | RESILIENCE
DEP-01 | Mobile Banking App | Payment Gateway API | Direct REST Call | High (Checkout Block) | Yes | Show friendly error retry modal | Optimal
DEP-02 | Payment Gateway | Notification SMS Service | Async Event Broker | Low (Delivery Delay) | Yes | Store in Dead Letter Queue (DLQ) | Optimal
DEP-03 | Order Service | Legacy Mainframe DB | Direct DB Driver | High (Order Stalled) | No | None (Hard failure) | At Risk

## EA Standards & Guardrails
📏 ENTERPRISE ARCHITECTURE STANDARDS, GUARDRAILS & GOVERNANCE
GUARDRAIL ID | ARCHITECTURE STANDARD RULE | DOMAIN | ENFORCEMENT MECHANISM | COMPLIANCE % | VIOLATING APPS COUNT | REMEDIATION DEADLINE | STATUS
STD-01 | Zero Direct Database Access Across Domain Services | Microservices | API Gateway & mTLS | 94% | 2 | 2026-11-30 | Compliant
STD-02 | All Production Workloads Must Run in OCI Containers | Cloud Platform | CI/CD Pipeline Linter | 98% | 1 | 2026-10-31 | Compliant
STD-03 | Structured OpenTelemetry Distributed Tracing | Observability | Base Docker Image SDK | 88% | 4 | 2026-12-15 | In Progress
STD-04 | All Secret Keys Must Reside in Vault / Cloud KMS | Security | Git Pre-Commit Hook | 100% | 0 | Continuous | Compliant

## Strategic EA Scorecard
🏆 STRATEGIC ENTERPRISE ARCHITECTURE MATURITY SCORECARD
PERSPECTIVE | STRATEGIC OBJECTIVE | TARGET KPI | ACTUAL ACHIEVED | WEIGHT | SCORE (0-100) | WEIGHTED SCORE | RAG STATUS
Cloud Modernization | Transition > 75% of application portfolio to cloud-native | >= 75.0% | 72.4% | 30% | 92 |  | Optimal
Tech Debt Elimination | Reduce annual technical debt financial drag by > 20% | >= 20.0% | 24.5% | 25% | 96 |  | Optimal
Architecture Standards | Achieve > 90% compliance with core EA guardrails | >= 90.0% |  | 20% | 95 |  | Optimal
API Reusability | Maintain average API reusability index >= 4.0 / 5.0 | >= 4.0 |  | 15% | 96 |  | Optimal
ARB Governance | Review 100% of major architectural blueprints in ARB | 100.0% | 100.0% | 10% | 98 |  | Optimal
OVERALL ENTERPRISE ARCHITECTURE MATURITY INDEX | [6 empty] | Elite (Grade A)