## Instructions
ENTERPRISE M&A TECH INTEGRATION, CARVE-OUT & DUE DILIGENCE MASTER
Mergers & Acquisitions Tech Playbook, Day 1/100 Milestones & TSA Navigation
Tujuan Dashboard |  | Mengawal integrasi teknologi paska akuisisi (Post-Merger Integration - PMI), pemisahan entitas (carve-out), dan due diligence siber: kesiapan sistem Day-1 & target Day-100, konsolidasi Active Directory & email domain, harmonisasi ERP & chart of accounts finansial, migrasi database pelanggan CRM, penyatuan jaringan cloud & data center, countdown perjanjian layanan transisi (TSA), realisasi sinergi penghematan biaya IT (synergies cost-out), hingga retensi talenta insinyur kunci.
Struktur 14 Sheet |  | 1. Instructions ¦ 2. Executive MA Integration Dash ¦ 3. Day-1 and Day-100 Milestones ¦ 4. Active Directory & Identity ¦ 5. ERP & Financial Harmonization ¦ 6. Customer CRM & Billing Migrate ¦ 7. Infra & Network Cloud Merge ¦ 8. IT TSA Contract & Countdown ¦ 9. IT Synergy Realization Cost ¦ 10. License Transfer & Rational ¦ 11. Target Cyber Due Diligence ¦ 12. Legacy Decommissioning Runway ¦ 13. IT Staff Retention & Talent ¦ 14. Strategic MA Scorecard
Automated Aggregation |  | Semua kartu KPI eksekutif, status countdown TSA, dan grafik pencapaian sinergi dihitung otomatis menggunakan formula Excel (COUNTA, COUNTIF, SUM, AVERAGE, IF).
Day-1 vs Day-100 Framework |  | Day-1 menjamin kelangsungan operasional tanpa gangguan (email bersama, akses VPN, komunikasi terpadu). Day-100 mengejar integrasi sistem inti finansial dan migrasi data awal.
TSA Cost Escalation |  | Perjanjian Transition Service Agreement (TSA) dari entitas penjual biasanya mengenakan penalti biaya berlipat ganda jika melewati batas waktu kontrak.
PANDUAN NAVIGASI WORKBOOK
No | Sheet Name | Domain & Kategori | Target Stakeholder | Key Metrics | Frekuensi Update
1 | Instructions | Governance & Guide | PMI Integration Committee | Panduan Schema & Standar M&A | Monthly
2 | Executive MA Integration Dash | Executive Cockpit | CIO / Head of Corporate Dev / CFO | Day-1 Readiness %, Synergies Run-rate, TSA | Weekly
3 | Day-1 and Day-100 Milestones | Milestone Tracking | M&A Integration Program Director | Critical Workstream Deliverables, Status | Weekly
4 | Active Directory & Identity | Identity & Collaboration | IAM Lead / Workplace Architect | Domain Trust, Mailbox Migration, SSO | Weekly
5 | ERP & Financial Harmonization | Enterprise Applications | ERP Lead / Finance Controller | GL CoA Mapping, Sub-ledger Consolidation | Bi-weekly
6 | Customer CRM & Billing Migrate | Commercial Customer Systems | CRM Lead / Billing Architect | Customer Records Cleansed, Deduplicated | Monthly
7 | Infra & Network Cloud Merge | Infrastructure & Network | Cloud Architect / Network Lead | AWS/Azure Tenant Migration, MPLS Link | Bi-weekly
8 | IT TSA Contract & Countdown | Contract & Legal Governance | IT Procurement / Corporate Legal | TSA Monthly Run Rate, Expiry Deadlines | Monthly
9 | IT Synergy Realization Cost | Financial Cost-Out | IT FinOps / CFO Office | Opex/Capex Savings Achieved vs Plan | Monthly
10 | License Transfer & Rational | Software Asset Management | License Compliance Manager | Duplicated SaaS Seats Eliminated, Novation | Monthly
11 | Target Cyber Due Diligence | Security & Risk Assessment | CISO / Cyber Due Diligence Lead | Vulnerabilities Remediated, Clean EDR | Monthly
12 | Legacy Decommissioning Runway | Application Retirement | Decommissioning PM / Enterprise Arch | Legacy Servers Powered-Off, Data Archived | Monthly
13 | IT Staff Retention & Talent | People & Organization | HR M&A Specialist / Tech Lead | Key Talent Retention Rate, Flight Risk | Monthly
14 | Strategic MA Scorecard | Annual Strategy & OKRs | Executive Board / CIO | Overall M&A Synergy Realization % | Quarterly

## Executive MA Integration Dash
EXECUTIVE M&A TECH INTEGRATION & SYNERGY VALUE COCKPIT
Day-1/Day-100 Progress, Realized Synergies Cost-Out, TSA Exit Health & Cyber Posture
KEY M&A TECH INTEGRATION & SYNERGY PERFORMANCE INDICATORS | [12 empty] | Synergy Stream | Target (IDR M) | Realized (IDR M)
DAY-1 READINESS |  | DAY-100 ON-TRACK % |  | TOTAL SYNERGIES (IDR M) |  | USERS INGESTED |  | CRM RECORDS MERGED |  | MONTHLY TSA OPEX (IDR M) | CYBER RISKS BURNED | KEY TECH RETENTION % | Software License C | 4800 | 5200
[13 empty] | Datacenter Closure | 6500 | 6800
All Cutover Deliverables Met |  | Major Workstreams Active |  | Realized Annual Run-Rate |  | Targetco Staff Ingested |  | Cleansed & Deduplicated |  | Target Zero by Day-120 | Clean EDR Deployed 100% | Zero Key Person Churn | IT Vendor Contract | 3600 | 3900
[13 empty] | Eliminate Overlapp | 2800 | 2900
[13 empty] | Telecommunications | 2200 | 2400
[13 empty] | Cybersecurity Tool | 1800 | 1850
[13 empty] | TSA Service | Monthly Fee
[13 empty] | Seller Datacenter | 850
[13 empty] | Seller Global SAP | 1200
[13 empty] | Seller Global Emai | 450
[13 empty] | Seller IT Service | 380
[13 empty] | Seller EDI Custome | 520
[13 empty] | Seller Global Cybe | 600
CRITICAL M&A INTEGRATION WATCHLIST & CARVE-OUT RUNWAY
Workstream / System Migration | Target Scope | Milestone Target Date | Current Progress % | TSA Exit / Synergy Impact | Key Person Lead | Audit State | Status
Targetco AD Forest Trust & O365 | Identity & Collaboration | 2026-08-15 | 90% | Terminates TSA-IT-03 | Budi Santoso | Audited | On Track
Oracle EBS to SAP S/4HANA GL Merge | Financial Harmonization | 2026-09-01 | 70% | Unlocks IDR 4.8B Synergies | Iwan Setiawan | Audited | On Track
Target AWS to Holding GCP VPC Merge | Cloud Infrastructure | 2026-08-31 | 60% | Terminates TSA-IT-01 | Rian Hidayat | Compliant | On Track
Salesforce B2B CRM Customer Merge | Commercial CRM Data | 2026-09-15 | 65% | 1.45M Clean Records Ingested | Ratna Juwita | Audited | On Track
CrowdStrike EDR Fleet Deployment | Cyber Due Diligence | 2026-06-01 | 100% | 100% Target Assets Cleaned | Fajar Nugraha | Certified | Completed
Software License Novation (M365/SF) | SaaS Rationalization | 2026-07-31 | 85% | IDR 3.3B Annual License Cut | Maya Pratiwi | Compliant | On Track
Seller IT Service Desk Handover | Support Operations | 2026-07-15 | 95% | Terminates TSA-IT-04 | Jessica Wong | Audited | On Track
Key Target Engineering Retention | Talent Organization | 2026-06-01 | 100% | 6 of 6 Key Leads Retained | CTO Office | Audited | Completed
| Monthly IT Synergies Realization & System Cutover Velocity (%) |  |  |  |  | M&A Tech Integration & Carve-Out Maturity
| Month | Target Synergies % | Actual Synergy Realized % | AD/IAM Domain Consolidation % |  | Operational Capability Pillar | Benchmark | Current Attainment
| May | 50 | 52.4 | 40 |  | Active Directory / O365 Merge | 4.2 | 4.8
| Jun | 58 | 61.2 | 48.5 |  | ERP Data Harmonization | 3.8 | 4.3
| Jul | 65 | 68.9 | 56 |  | Network SD-WAN Interlink | 4 | 4.6
| Aug | 65 | 67.5 | 55 |  | SaaS License Optimization | 4.2 | 4.7
| Sep | 75 | 79.2 | 68 |  | Cybersecurity TSA Clearance | 4 | 4.5
| Oct | 85 | 89.5 | 80 |  | Change Management Org Sync | 3.8 | 4.2
| M&A IT Synergies Realization Waterfall (Million USD) |  |  |  |  | Day-1 TSA Milestones Completed vs System Integration Score (%)
| Synergy Lever | Base Level | Variance Delta | Cumulative Bridge |  | Month | TSA Closed | Integration % | Target %
| Target IT Baseline | 0 | 65 | 65 |  | M1 | 14 | 25 | 20
| ERP Consolidation | 65 | -12.5 | 52.5 |  | M2 | 28 | 45 | 40
| Data Center Exit | 52.5 | -9.8 | 42.7 |  | M3 | 42 | 68 | 60
| Network & Telco Harmonize | 42.7 | -6.4 | 36.3 |  | M4 | 56 | 82 | 75
| Carve-out Transitional TSA | 36.3 | 4.2 | 40.5 |  | M5 | 68 | 92.5 | 90
| Post-Merger Run-Rate | 0 | 40.5 | 40.5 |  | M6 | 75 | 98.4 | 95

## Day-1 and Day-100 Milestones
M&A TECH INTEGRATION DAY-1 & DAY-100 CRITICAL MILESTONES
Workstream Deliverables, Go-Live Cutover Readiness & Executive Sign-off
Milestone ID | Integration Workstream | Key Deliverable Name | Target Horizon | Planned Due Date | Completion % | Workstream Lead | RAG Status | Executive Sponsor
ML-D1-01 | Identity & Collaboration | Global Address List (GAL) Unified Sync | Day-1 Critical | 2026-06-01 | 100% | Budi Santoso | Completed | VP Digital Workplace
ML-D1-02 | Network & Connectivity | Inter-Office Cross-Connect IPSec VPN Mesh | Day-1 Critical | 2026-06-01 | 100% | Rian Hidayat | Completed | VP Infrastructure
ML-D1-03 | Cybersecurity Incident Resp | Deploy Corporate EDR (CrowdStrike) on Target Fleet | Day-1 Critical | 2026-06-01 | 100% | Fajar Nugraha | Completed | CISO
ML-D1-04 | IT Service Desk Alignment | Unified Service Desk Routing & VIP Escalation | Day-1 Critical | 2026-06-01 | 100% | Jessica Wong | Completed | Head of Support
ML-D1-05 | Financial Chart of Accounts | Intercompany Settlement & Treasury Mapping | Day-1 Critical | 2026-06-01 | 100% | Iwan Setiawan | Completed | CFO
ML-D100-01 | Email Tenant Migration | Target O365 Tenant Merged into Corporate Cloud | Day-100 Horizon | 2026-08-15 | 85% | Budi Santoso | On Track | VP Digital Workplace
ML-D100-02 | ERP Ledger Consolidation | Target Oracle ERP Harmonized into SAP S/4HANA | Day-100 Horizon | 2026-09-01 | 70% | Iwan Setiawan | On Track | Head of Enterprise Apps
ML-D100-03 | Customer Data Cleansing | Target CRM Deduplicated & Merged into Salesforce | Day-100 Horizon | 2026-09-15 | 65% | Ratna Juwita | On Track | Chief Commercial Officer
ML-D100-04 | Cloud Tenant Migration | Target AWS Workloads Migrated to Core GCP VPC | Day-100 Horizon | 2026-09-30 | 60% | Rian Hidayat | On Track | VP Cloud Engineering
ML-D100-05 | Vendor Contract Novation | Consolidate 120 Software Vendor Licenses | Day-100 Horizon | 2026-09-30 | 75% | Maya Pratiwi | On Track | Head of IT Procurement

## Active Directory & Identity
ACTIVE DIRECTORY, SSO DOMAIN TRUST & MAILBOX MIGRATION
Target AD Forest Consolidation, Entra ID Cloud Sync, Mailboxes & MFA Enrollment
Entity / Domain ID | Source AD Domain | Target AD Domain | Total User Accounts | Mailboxes Migrated | Migration Progress % | MFA Enrolled % | Domain Trust State | Status
DOM-01 | targetco.internal | corp.holding.com | 2400 | 2400 | 100% | 99% | Two-Way Forest Trust | Completed
DOM-02 | targetlogistics.local | corp.holding.com | 1200 | 1080 | 90% | 95% | Two-Way Forest Trust | In Progress
DOM-03 | targetfintech.co.id | corp.holding.com | 850 | 720 | 85% | 98% | Selective Auth Trust | In Progress
DOM-04 | targetvietnam.vn | corp.holding.com | 450 | 315 | 70% | 92% | Selective Auth Trust | In Progress
DOM-05 | targetphilippines.ph | corp.holding.com | 380 | 210 | 55% | 88% | One-Way Trust | In Progress

## ERP & Financial Harmonization
ERP FINANCIAL LEDGER HARMONIZATION & CHART OF ACCOUNTS (COA)
Mapping Target General Ledger to Corporate SAP S/4HANA Group Chart of Accounts
Sub-Ledger ID | Source System / Module | Corporate Target Ledger | Accounts Mapped | Historical Data Cutover Years | Reconciliation Discrepancy | Cutover Testing Status | Lead Accounting Architect
FIN-01 | Oracle EBS General Ledger (GL) | SAP S/4HANA Universal Journal (ACDOCA) | 850 | 1900-01-04 | 0 | Validated & Reconciled | Iwan Setiawan, Ak
FIN-02 | Oracle EBS Accounts Payable (AP) | SAP S/4HANA FI-AP Open Items | 3200 | 1900-01-02 | 0 | Validated & Reconciled | Iwan Setiawan, Ak
FIN-03 | Oracle EBS Accounts Receivable (AR) | SAP S/4HANA FI-AR Customer Sub-ledger | 4500 | 1900-01-02 | 0 | Validated & Reconciled | Ratna Juwita, SE
FIN-04 | Target Fixed Asset Register (FA) | SAP S/4HANA Asset Accounting (FI-AA) | 1250 | 1900-01-06 | 0 | Validated & Reconciled | Iwan Setiawan, Ak
FIN-05 | Target Inventory & Material Ledger | SAP S/4HANA MM/CO-PC Valuated | 18500 | 1900-01-01 | 0 | In User Acceptance Test | Dedi Prasetyo
FIN-06 | Treasury Bank Master Accounts | SAP Cash Management Bank Ledger | 48 | 1900-01-04 | 0 | Validated & Reconciled | Ratna Juwita, SE

## Customer CRM & Billing Migrate
CUSTOMER CRM, MASTER DATA CLEANSING & BILLING MIGRATION
Target HubSpot/SugarCRM Migration into Corporate Salesforce & Amdocs Billing Sync
Dataset ID | Customer Data Domain | Source Records | Deduplicated Valid Records | Data Quality Match % | Migrated to Core CRM | Migration % | Cutover Status
CRM-01 | B2B Enterprise Accounts | 12500 | 11800 | 98.5% | 11800 | 100% | Completed
CRM-02 | B2B Contact Decision Makers | 38000 | 34500 | 96.2% | 34500 | 100% | Completed
CRM-03 | B2C Consumer Customer Profiles | 1450000 | 1380000 | 97.8% | 1150000 | 83.3% | In Progress
CRM-04 | Active Contracts & Subscriptions | 85000 | 84200 | 99.4% | 72000 | 85.5% | In Progress
CRM-05 | Historical Invoices & Billing Tx | 5200000 | 5200000 | 100% | 4800000 | 92.3% | In Progress
CRM-06 | Open Support Tickets & Cases | 18500 | 17200 | 95.5% | 17200 | 100% | Completed

## Infra & Network Cloud Merge
INFRASTRUCTURE, DATACENTER & MULTI-CLOUD MERGE ARCHITECTURE
Target AWS/Azure/On-Prem Workloads Consolidation into Corporate Multi-Cloud Mesh
Infra Batch ID | Source Infrastructure Asset | Workload Description | Target Landing Zone | Migration Strategy (6-R) | VMs / Instances | Cutover Due Date | Execution Status
INF-01 | Target On-Prem Colocation Racks | Legacy Database & File Servers | Holding Cikarang DC | Rehost (Lift & Shift) | 120 | 2026-07-31 | In Progress
INF-02 | Target AWS Standalone Account | Core E-Commerce Kubernetes Pods | Holding GCP Primary VPC | Replatform (Container Mesh) | 85 | 2026-08-31 | In Progress
INF-03 | Target Azure Corporate Tenant | Internal Legacy Web Applications | Holding Corporate Cloud | Refactor (Serverless Cloud) | 45 | 2026-09-15 | Testing
INF-04 | Target Office Branch Routers | 28 Regional Branch MPLS Lines | Corporate SD-WAN Network | Replatform (Meraki SD-WAN) | 28 | 2026-07-15 | Completed
INF-05 | Target On-Premises SAN Storage | Archived Transaction Blobs (120TB) | AWS S3 Glacier Deep Archive | Retain / Rehost Cold Data | 1 | 2026-08-15 | Completed
INF-06 | Target VMware Virtual Farm | Internal Dev/QA Environments | Holding Shared K8s Dev Farm | Repurchase / Decommission | 60 | 2026-09-30 | Planning

## IT TSA Contract & Countdown
TRANSITION SERVICE AGREEMENT (TSA) GOVERNANCE & EXIT COUNTDOWN
Seller TSA Services, Monthly Fee Run-Rate, Exit Readiness & Penalty Prevention
TSA Schedule ID | Service Provided by Seller | Monthly TSA Fee (IDR M) | Contract Expiry Date | Days Remaining to Exit | Exit Project Status | Replacement System Ready? | Exit Program Lead
TSA-IT-01 | Seller Datacenter Hosting & Infrastructure | 850 | 2026-08-31 | 1900-03-15 | Migration in Progress | Yes (Cikarang Staging Active) | Rian Hidayat
TSA-IT-02 | Seller Global SAP ERP Instance Access | 1200 | 2026-09-30 | 1900-04-14 | GL Mapping in Progress | Yes (SAP S/4 Staging) | Iwan Setiawan
TSA-IT-03 | Seller Global Email & Active Directory | 450 | 2026-07-31 | 1900-02-13 | Mailbox Cutover Imminent | Yes (Holding O365 Ready) | Budi Santoso
TSA-IT-04 | Seller IT Service Desk & End-User Support | 380 | 2026-07-15 | 1900-01-29 | Knowledge Transfer Complete | Yes (Holding Service Desk Live) | Jessica Wong
TSA-IT-05 | Seller EDI Customer Ordering Gateway | 520 | 2026-08-15 | 1900-02-27 | Partner Testing Active | Yes (Corporate MuleSoft ESB) | Dedi Susanto
TSA-IT-06 | Seller Global Cybersecurity SOC Service | 600 | 2026-06-30 | 1900-01-14 | SOC Transition Complete | Yes (Corporate 24/7 SOC) | Fajar Nugraha

## IT Synergy Realization Cost
M&A IT COST SYNERGY REALIZATION & VALUE CREATION RUNWAY
Annual Recurring IT Opex/CapEx Cost-Out Realized (IDR Millions)
Synergy ID | Synergy Initiative / Cost-Out Category | Target Baseline Spend (IDR M) | Target Annual Synergy (IDR M) | Realized Run-Rate Savings (IDR M) | Variance (IDR M) | Achievement % | Status
SYN-01 | Software License Consolidation (ERP & CRM) | 14500 | 4800 | 5200 |  |  | Completed
SYN-02 | Datacenter Closure & Cloud Rehosting | 18200 | 6500 | 6800 |  |  | Completed
SYN-03 | IT Vendor Contracting & Volume Discount | 12000 | 3600 | 3900 |  |  | Completed
SYN-04 | Eliminate Overlapping IT Management & Tools | 8500 | 2800 | 2900 |  |  | Completed
SYN-05 | Telecommunications MPLS to SD-WAN | 6400 | 2200 | 2400 |  |  | Completed
SYN-06 | Cybersecurity Tooling Rationalization (EDR/SIEM) | 5200 | 1800 | 1850 |  |  | Completed
SYN-07 | TSA Exit Fee Elimination (Seller Run-Rate) | 48000 | 48000 | 32000 |  |  | In Progress
TOTAL IT COST SYNERGIES REALIZED | [6 empty] | HIGH REALIZATION

## License Transfer & Rational
SOFTWARE LICENSE NOVATION, TRANSFER & DUPLICATION AUDIT
SaaS License Rationalization, Duplicated Vendor Contracts & Transfer Savings
License ID | Software Application Name | Target Contract Status | Duplicated Seats | Corporate Agreement Novation | Annual Savings (IDR M) | Legal Novation Status | Owner
LIC-RAT-01 | Microsoft 365 E5 Suite | Targetco Tenant Novated | 2400 | Enterprise Agreement Co-term | 1850 | Novated & Signed | Maya Pratiwi
LIC-RAT-02 | Salesforce CRM Enterprise | Targetco Tenant Merged | 450 | Master Service Agreement | 1450 | Novated & Signed | Maya Pratiwi
LIC-RAT-03 | Zoom Enterprise Video | Decommissioned (Standardize on Teams) | 1200 | Cancelled at Renewal | 420 | Contract Terminated | Maya Pratiwi
LIC-RAT-04 | Slack Enterprise Grid | Decommissioned (Standardize on Teams) | 850 | Cancelled at Renewal | 380 | Contract Terminated | Maya Pratiwi
LIC-RAT-05 | CrowdStrike Falcon Complete | Merged into Holding Fleet | 3200 | Holding Volume Discount Add | 920 | Novated & Signed | Maya Pratiwi
LIC-RAT-06 | Atlassian Jira / Confluence Cloud | Targetco Cloud Migrated | 650 | Holding Atlassian Access Tier | 480 | Novated & Signed | Maya Pratiwi

## Target Cyber Due Diligence
TARGET COMPANY CYBERSECURITY DUE DILIGENCE & REMEDIATION
Vulnerability Assessment, Clean EDR Coverage, Active Directory Exposure & Risk Burn-down
Audit Finding ID | Cyber Risk Category | Identified Threat / Exposure | Target Asset Scope | CVSS Severity Score | Remediation Action Taken | Clean EDR Deployed? | Remediation Status
CYB-DD-01 | Identity & Credentials | Legacy AD NTLMv1 Auth Enabled & Weak Hashes | targetco.internal Domain Controllers | 9.2 | Enforced Kerberos & Disabled NTLMv1 | Yes (100%) | Remediated
CYB-DD-02 | Endpoint Security | Unmanaged Laptops Without Corporate Antivirus | 320 Remote Sales Laptops | 8.8 | Enrolled in CrowdStrike & Intune Wipe | Yes (100%) | Remediated
CYB-DD-03 | Perimeter Network | Open RDP Port 3389 Exposed to Public Internet | Office Gateway Firewall | 9.8 | Immediate Firewall Port Closure & VPN Mandate | Yes (100%) | Remediated
CYB-DD-04 | Cloud Storage Exposure | Publicly Accessible S3 Bucket with Customer Invoices | Target AWS Account | 8.5 | Applied S3 Block Public Access & KMS Encrypt | Yes (100%) | Remediated
CYB-DD-05 | Vulnerability Patching | Unpatched Log4j in Legacy Customer Portal | Customer Tomcat Web Servers | 9.5 | Patched Java Libraries to Log4j v2.22 | Yes (100%) | Remediated
CYB-DD-06 | Database Encryption | Customer PII Database Unencrypted at Rest | Oracle EBS Customer Database | 7.8 | Enabled Oracle Transparent Data Encryption (TDE) | Yes (100%) | Remediated

## Legacy Decommissioning Runway
TARGET LEGACY SYSTEM DECOMMISSIONING & DATA ARCHIVAL RUNWAY
Decommissioned Servers, Database Sanitization, Hardware Disposal & Power Off
Decom ID | Legacy Application Name | Original Host Platform | Data Archived to S3 / Cold | Physical / Virtual Hosts | Power-Off Due Date | Annual Opex Avoided (IDR M) | Decommissioning State
DEC-01 | Targetco Custom ERP Accounting | HP ProLiant Rack Servers | Archived (Compliant 10 yrs) | 12 | 2026-09-30 | 950 | Scheduled
DEC-02 | SugarCRM B2B Customer Portal | VMware Virtual Machines | Archived (Compliant 7 yrs) | 6 | 2026-08-31 | 420 | Scheduled
DEC-03 | Zimbra Open Source Email Server | Dell PowerEdge Rack Servers | All Mailboxes in O365 | 8 | 2026-07-31 | 580 | In Progress
DEC-04 | Legacy Apache PHP Customer Shop | AWS EC2 Standalone | Database Exported to S3 | 14 | 2026-09-15 | 820 | Scheduled
DEC-05 | Target On-Premise PBX Phone Switch | Avaya Hardware Switch | Migrated to MS Teams Phone | 2 | 2026-06-30 | 350 | Completed
DEC-06 | Legacy VPN Concentrator Appliance | Cisco ASA 5520 | Replaced with Zscaler ZPA | 4 | 2026-06-15 | 280 | Completed

## IT Staff Retention & Talent
TARGET IT TALENT RETENTION, KEY PERSON RISK & INTEGRATION ROLES
Targetco Engineering Retention Packages, Talent Mapping & Integration Assignment
Staff ID | Role / Technical Domain | Assigned Integration Stream | Targetco Employment Level | Retention Package Signed? | Flight Risk Level | New Corporate Mapping Title | Integration Status
STF-01 | Chief Technology Officer (Targetco) | PMI Senior Technical Advisor | C-Level Executive | Yes (24-Month Stay Bonus) | Low | VP Technology M&A | Retained & Active
STF-02 | Principal Cloud Architect | Cloud Tenant Merge (AWS to GCP) | Principal Staff | Yes (18-Month Stay Bonus) | Low | Principal Cloud Architect | Retained & Active
STF-03 | Lead Database Administrator (Oracle) | ERP Financial Harmonization | Senior Specialist | Yes (12-Month Stay Bonus) | Low | Lead Database Specialist | Retained & Active
STF-04 | Senior Backend Engineer (Go/Node) | Core Microservice Ingestion | Senior Engineer | Yes (Retention Stock RSUs) | Low | Senior Software Engineer | Retained & Active
STF-05 | Senior Information Security Analyst | Cyber Due Diligence & EDR | Senior Specialist | Yes (Retention Stock RSUs) | Low | Senior Security Engineer | Retained & Active
STF-06 | WMS & Logistics Systems Lead | Supply Chain IT Integration | Lead Specialist | Yes (18-Month Stay Bonus) | Low | Head of Warehouse IT | Retained & Active

## Strategic MA Scorecard
STRATEGIC M&A TECH INTEGRATION & VALUE CREATION SCORECARD
Annual OKRs, Day-1/100 Completion, Total IT Synergies & TSA Exit Rate
Scorecard ID | Strategic Objective | Key M&A Tech Metric | Target Benchmark | Actual Value | Variance | Achievement % | Status | Executive Owner
OKR-MA-01 | Day-1 Execution | Day-1 Critical Milestones Delivered (%) | 100 | 100 |  |  |  | M&A Program Director
OKR-MA-02 | Day-100 Momentum | Day-100 Integration Milestones on Track (%) | 75 | 85 |  |  |  | PMI Workstream Leads
OKR-MA-03 | Synergy Realization | Total Annual IT Cost Synergies (IDR Billions) | 60 | 71 |  |  |  | Chief Financial Officer
OKR-MA-04 | Identity Consolidation | Target Users Migrated to Holding AD/O365 (%) | 90 | 94.5 |  |  |  | VP Digital Workplace
OKR-MA-05 | Financial Harmonization | Target Financial Accounts Mapped to SAP (%) | 100 | 100 |  |  |  | Head of Enterprise Applications
OKR-MA-06 | TSA Contract Exit | TSA Services Exited Before Penalty Window (%) | 100 | 100 |  |  |  | Corporate Legal Counsel
OKR-MA-07 | Cyber Due Diligence | Critical Due Diligence Risks Remediated (%) | 100 | 100 |  |  |  | Chief Information Security Officer
OKR-MA-08 | Key Talent Retention | Critical In-Scope Tech Talent Retained (%) | 90 | 100 |  |  |  | Chief Technology Officer
OKR-MA-09 | License Rationalization | Duplicated Software Seats Terminated (%) | 80 | 88 |  |  |  | Head of IT Procurement
OKR-MA-10 | Legacy Decommission | Target Legacy Hosts Powered Down on Schedule | 30 | 46 |  |  |  | Infrastructure Operations Lead