## Instructions
📊 IT PMO & AGILE PORTFOLIO DELIVERY ALL-IN-ONE ENTERPRISE DASHBOARD
Enterprise-grade IT Project Management Office (PMO) governance, stage-gate tracking, and EVM budget delivery.
NO | SHEET NAME | DOMAIN / MODULE | KEY METRICS TRACKED | FORMULA AUTOMATION LEVEL
1 | Executive PMO Dashboard | Executive Portfolio Delivery | Active Projects, Capex Budget, On-Time Delivery %, Critical RAID | 100% Dynamic Formula Driven
2 | Portfolio Stage-Gate | Stage-Gate Pipeline | Ideation, Business Case, Execution, UAT, Go-Live Milestones | Automated Gate RAG Status
3 | Project Milestone Log | Milestone Tracking & Variance | Baseline vs Forecast Dates, Schedule Slippage (Days), Critical Path | Date Variance Formulas
4 | Agile Sprints & Delivery | Squad Velocity & Predictability | Story Points Committed vs Delivered, Sprint Predictability % | Dynamic Sprint Velocity
5 | Enterprise RAID Log | Risk, Issue & Dependency | Probability × Impact Matrix, Mitigation Strategy, Action Owners | Weighted Risk Scores
6 | Resource Capacity Heatmap | Capacity & Allocation | Assigned FTE %, Over-Allocation Alerts, Billable Consulting Hours | Capacity Utilization %
7 | Project Budgets vs Actual | Earned Value Management (EVM) | Budget At Completion (BAC), Actual Cost (AC), CPI & SPI Index | EVM Formula Calculations
8 | Change Request (CR) Governance | Scope & Budget Variations | Cost Impact ($), Schedule Impact (Days), CCB Approvals | Aggregated Impact Totals
9 | Vendor Deliverable SOW | Vendor & Partner Milestones | SOW Deliverables, Acceptance Sign-off, Retainage Release | Contract Fulfillment %
10 | Steering Committee Updates | Executive Governance | Monthly Highlights, Red Flags, Decisions Required by SteerCo | RAG Status Consolidation
11 | Benefits & ROI Realization | Value Delivery & Business Cases | Expected Annual Value, Realized Savings, Payback Period | ROI & Payback Calculations
12 | Quality Gates & UAT | Release Readiness | SIT / UAT Pass Rate %, Blocker Defect Count, Go/No-Go Decision | Pass Rate Metrics
13 | Strategic PMO Scorecard | PMO Maturity & Performance | On-Time, On-Budget, Customer Satisfaction, Strategic Fit | Weighted Index Formula

## Executive PMO Dashboard
📊 IT PMO & AGILE PORTFOLIO DELIVERY EXECUTIVE DASHBOARD
Real-time enterprise IT project portfolio tracking, budget delivery, schedule health, and stage-gate readiness.
TOTAL ACTIVE PROJECTS |  |  | PORTFOLIO CAPEX BUDGET |  |  | ACTUAL SPEND TO DATE |  |  | PROJECTS ON-TRACK %
AVG CPI (COST INDEX) |  |  | CRITICAL OPEN RISKS |  |  | AGILE PREDICTABILITY % |  |  | EXPECTED ROI REALIZED
PROJECT BUDGET VS ACTUAL BY DOMAIN | [6 empty] | PORTFOLIO STAGE DISTRIBUTION
Domain | Budget ($) | Actual ($) |  |  |  |  | Stage | Projects
Core Banking & FinTech | 2500000 | 1850000 |  |  |  |  | Execution
Cloud Infrastructure | 1800000 | 1420000 |  |  |  |  | Testing / UAT
Data & Analytics BI | 1200000 | 890000 |  |  |  |  | Planning
Digital Workplace | 950000 | 720000 |  |  |  |  | Completed
Cybersecurity & GRC | 1400000 | 1150000
TOP STRATEGIC IT INITIATIVES WATCHLIST
PROJECT ID | PROJECT NAME | EXECUTIVE SPONSOR | STAGE | BUDGET ($) | ACTUAL ($) | VARIANCE ($) | RAG STATUS
PRJ-101 | Core Banking Cloud Migration | CIO Office | Execution
PRJ-102 | Next-Gen Mobile App v4.0 | VP Digital | Testing / UAT
PRJ-103 | Data Lakehouse Real-time Streaming | Head of Data | Execution
PRJ-104 | Zero Trust Identity Architecture | CISO Office | Execution
PRJ-105 | Enterprise ERP SAP S/4HANA Upgrade | CFO Office | Planning
| Monthly Project Milestone Velocity & Budget SPI/CPI Trajectory |  |  |  |  | Enterprise PMO & Strategic Delivery Index
| Month | Target CPI Score | Actual Cost Perf Index | Milestone On-Time Rate % |  | Operational Capability Pillar | Benchmark | Current Attainment
| May | 1 | 1.02 | 88 |  | Stage-Gate Governance | 4.2 | 4.8
| Jun | 1 | 1.04 | 90.5 |  | Resource Capacity Allocation | 4 | 4.5
| Jul | 1 | 1.06 | 93 |  | Earned Value EVM Tracking | 4.2 | 4.7
| Aug | 1 | 1.05 | 92.4 |  | Cross-Project Dependency Map | 3.8 | 4.4
| Sep | 1 | 1.08 | 95.5 |  | Executive Risk Escalation | 4 | 4.6
| Oct | 1 | 1.1 | 97.8 |  | Agile / Waterfall Hybrid Mgt | 4 | 4.5
| Strategic IT Capital Allocation by Transformation Pillar ($M) |  |  |  |  | Project Schedule Variance (SPI) vs Cost Performance Index (CPI)
| Month | Cloud & Modernization | Data & AI Intelligence | Cybersecurity & Zero Trust | Customer Experience | Strategic Program | Schedule SPI | Cost CPI | Budget ($M)
| May | 4.2 | 2.8 | 2.1 | 1.8 | Core ERP Upgrade | 1.05 | 1.02 | 14.5
| Jun | 4.5 | 3.1 | 2.3 | 1.9 | Cloud Migration Wave 3 | 0.98 | 1.04 | 8.2
| Jul | 5 | 3.6 | 2.5 | 2.1 | Omnichannel POS Rollout | 1.08 | 0.97 | 6.8
| Aug | 4.9 | 3.5 | 2.4 | 2 | Zero Trust Security Revamp | 1.02 | 1.01 | 5.4
| Sep | 5.5 | 4.2 | 2.8 | 2.4 | Data Mesh Analytics Hub | 1.12 | 1.06 | 7.5
| Oct | 6.2 | 4.8 | 3.2 | 2.7 | Customer AI Assistant | 1.15 | 1.08 | 4.2

## Portfolio Stage-Gate
🚀 IT PROJECT PORTFOLIO PIPELINE & STAGE-GATE GOVERNANCE
| Total Projects: |  |  | Projects On Track:
PROJECT ID | PROJECT NAME | EXECUTIVE SPONSOR | PROJECT MANAGER | CURRENT STAGE | GATE STATUS | TARGET GO-LIVE | RAG HEALTH | COMPLETION % | PRIORITY
PRJ-101 | Core Banking Cloud Migration | CIO Office | Bambang Wijaya | Execution | Approved | 2026-12-15 | On Track | 72% | High
PRJ-102 | Next-Gen Mobile App v4.0 | VP Digital | Dewi Lestari | Testing / UAT | Approved | 2026-11-20 | On Track | 88% | Critical
PRJ-103 | Data Lakehouse Real-time Streaming | Head of Data | Rian Hidayat | Execution | Approved | 2026-12-30 | On Track | 65% | High
PRJ-104 | Zero Trust Identity Architecture | CISO Office | Aditya Nugraha | Execution | Approved | 2027-01-31 | On Track | 55% | High
PRJ-105 | Enterprise ERP SAP S/4HANA Upgrade | CFO Office | Siti Aminah | Planning | In Review | 2027-06-30 | At Risk | 25% | Critical
PRJ-106 | Global CRM Salesforce Integration | VP Sales | Kevin Pratama | Execution | Approved | 2026-11-30 | On Track | 80% | Medium
PRJ-107 | Omnichannel Customer Portal | VP Operations | Maya Putri | Testing / UAT | Approved | 2026-11-15 | On Track | 90% | High
PRJ-108 | DevOps Automated Release Train | Head of Eng | Fajar Ramadhan | Execution | Approved | 2026-12-10 | On Track | 70% | Medium

## Project Milestone Log
🎯 PROJECT MILESTONE SCHEDULE, BASELINE & SLIPPAGE (DAYS)
MILESTONE ID | PROJECT NAME | MILESTONE DELIVERABLE | BASELINE DATE | FORECAST DATE | VARIANCE (DAYS) | CRITICAL PATH | OWNER | STATUS
MS-101 | Core Banking Cloud Migration | Database Schema Conversion Complete | 2026-08-30 | 2026-08-28 |  | Yes | Cloud Team | Completed
MS-102 | Core Banking Cloud Migration | Application Multi-Region Staging | 2026-10-15 | 2026-10-15 |  | Yes | Cloud Team | On Track
MS-103 | Next-Gen Mobile App v4.0 | Security Penetration Testing Sign-off | 2026-10-25 | 2026-10-27 |  | Yes | QA & SecOps | In Review
MS-104 | Next-Gen Mobile App v4.0 | App Store & Play Store Submission | 2026-11-10 | 2026-11-10 |  | Yes | Mobile Pod | On Track
MS-105 | Data Lakehouse Real-time Streaming | CDC Pipeline Production Cutover | 2026-11-15 | 2026-11-20 |  | No | Data Ops | In Review

## Agile Sprints & Delivery
🏃 AGILE SPRINT VELOCITY, PREDICTABILITY & STORY POINTS
Avg Predictability %:
POD / SQUAD NAME | PROJECT NAME | SPRINT CADENCE | POINTS COMMITTED | POINTS DELIVERED | POINTS SPILLED | PREDICTABILITY % | VELOCITY TREND | STATUS
FinTech Squad Alpha | Core Banking Cloud Migration | Sprint 24 | 85 | 82 |  |  | Increasing | Optimal
Mobile Experience Pod | Next-Gen Mobile App v4.0 | Sprint 18 | 65 | 60 |  |  | Stable | Optimal
Data Pipeline Guild | Data Lakehouse Real-time Streaming | Sprint 12 | 70 | 68 |  |  | Increasing | Optimal
SecOps Squad | Zero Trust Identity Architecture | Sprint 10 | 50 | 42 |  |  | Fluctuating | At Risk
Enterprise ERP Team | Enterprise ERP SAP S/4HANA Upgrade | Sprint 6 | 55 | 45 |  |  | Decreasing | At Risk

## Enterprise RAID Log
⚠️ ENTERPRISE RAID REGISTER (RISKS, ASSUMPTIONS, ISSUES, DEPENDENCIES)
Critical/High Items:
RAID ID | TYPE | PROJECT NAME | ITEM DESCRIPTION | PROBABILITY | IMPACT | RISK SCORE | MITIGATION STRATEGY | ACTION OWNER | STATUS
RD-01 | Risk | Core Banking Cloud Migration | Database failover latency exceeds 50ms during cutover | Medium | High | High | Conduct dry-run cutover on replica staging cluster | Cloud Arch | Monitoring
RD-02 | Dependency | Next-Gen Mobile App v4.0 | Third-party KYC API vendor sandbox delay | High | High | High | Escalate to vendor VP and implement mocked responses | Dewi Lestari | In Progress
RD-03 | Issue | Enterprise ERP SAP S/4HANA Upgrade | Legacy COBOL interface documentation missing | High | High | High | Engage external mainframe consulting firm | Siti Aminah | In Progress
RD-04 | Risk | Data Lakehouse Real-time Streaming | CDC log retention storage exhaustion on source DB | Low | Medium | Medium | Configure auto-scaling log volume alerts | Data Ops | Mitigated
RD-05 | Assumption | Zero Trust Identity Architecture | All employees have corporate-managed mobile authenticator | Low | Low | Low | Deploy self-service hardware token option | SecOps | Closed

## Resource Capacity Heatmap
👥 PMO RESOURCE CAPACITY, ALLOCATION & OVER-ALLOCATION HEATMAP
RESOURCE NAME | ROLE / SPECIALIZATION | PRIMARY PROJECT | SECONDARY PROJECT | ALLOCATED FTE % | MONTHLY HOURS | CAPACITY STATUS | LOCATION | STATUS
Bambang Wijaya | Senior Solutions Architect | Core Banking Cloud Migration | None | 100% | 160 | Optimal | Jakarta | Active
Dewi Lestari | Lead Project Manager | Next-Gen Mobile App v4.0 | Omnichannel Portal | 120% | 192 | Over-Allocated | Jakarta | Active
Rian Hidayat | Lead Data Engineer | Data Lakehouse Streaming | None | 90% | 144 | Optimal | Bandung | Active
Aditya Nugraha | Cybersecurity Architect | Zero Trust Identity | Core Banking | 115% | 184 | Over-Allocated | Jakarta | Active
Siti Aminah | ERP Functional Consultant | Enterprise ERP Upgrade | None | 100% | 160 | Optimal | Surabaya | Active

## Project Budgets vs Actual
💰 EARNED VALUE MANAGEMENT (EVM), CAPEX BUDGET & COST PERFORMANCE
| Total Portfolio Budget: |  |  | Total Actual Spend:
PROJECT ID | PROJECT NAME | FUNDING TYPE | BUDGET BAC ($) | ACTUAL COST AC ($) | VARIANCE ($) | CPI (COST INDEX) | SPI (SCHED INDEX) | EVM HEALTH | FINANCIAL STATUS
PRJ-101 | Core Banking Cloud Migration | Capex | 1850000 | 1420000 |  | 1.05 | 1.02 | Optimal | Under Budget
PRJ-102 | Next-Gen Mobile App v4.0 | Capex | 950000 | 840000 |  | 1.02 | 0.98 | Optimal | On Track
PRJ-103 | Data Lakehouse Real-time Streaming | Capex | 1200000 | 890000 |  | 1.08 | 1.01 | Optimal | Under Budget
PRJ-104 | Zero Trust Identity Architecture | Capex | 780000 | 520000 |  | 1.04 | 1 | Optimal | Under Budget
PRJ-105 | Enterprise ERP SAP S/4HANA Upgrade | Capex | 3200000 | 850000 |  | 0.92 | 0.88 | At Risk | Over Budget

## Change Request Governance
📝 CHANGE REQUEST (CR) LOG & SCOPE VARIATION GOVERNANCE
CR ID | PROJECT NAME | CHANGE DESCRIPTION | COST IMPACT ($) | SCHEDULE IMPACT (DAYS) | REASON FOR CHANGE | CCB APPROVAL | STATUS | DECISION DATE
CR-101 | Core Banking Cloud Migration | Add read-replica in secondary region for disaster recovery | 45000 | 14 | Security & Compliance Mandate | Approved | Implemented | 2026-09-10
CR-102 | Next-Gen Mobile App v4.0 | Biometric face liveness verification integration | 28000 | 7 | Fraud Prevention Policy | Approved | In Progress | 2026-09-25
CR-103 | Enterprise ERP SAP S/4HANA Upgrade | Custom logistics warehouse reporting module | 65000 | 30 | Scope Creep from Business Unit | In Review | Evaluating | 2026-10-05

## Vendor Deliverable SOW
🤝 VENDOR SOW DELIVERABLES, ACCEPTANCE & RETAINAGE
SOW ID | VENDOR NAME | PROJECT NAME | MILESTONE DELIVERABLE | CONTRACT VALUE ($) | DUE DATE | ACCEPTANCE SIGN-OFF | RETAINAGE ($) | STATUS
SOW-01 | Accenture Cloud Services | Core Banking Cloud Migration | Infrastructure as Code Staging Repo | 250000 | 2026-08-31 | Accepted | 25000 | Approved
SOW-02 | Thoughtworks Digital | Next-Gen Mobile App v4.0 | Core Design System & Flutter Architecture | 180000 | 2026-09-30 | Accepted | 18000 | Approved
SOW-03 | Infosys Enterprise | Enterprise ERP SAP Upgrade | Blueprinting & Data Migration Scripts | 420000 | 2026-10-31 | In Review | 42000 | In Review

## Steering Committee Updates
🏛️ STEERING COMMITTEE (STEERCO) EXECUTIVE GOVERNANCE LOG
PROJECT ID | PROJECT NAME | EXECUTIVE SPONSOR | KEY MILESTONES ACHIEVED | RED FLAGS / ESCALATIONS | DECISIONS REQUIRED | NEXT REVIEW DATE | RAG HEALTH
PRJ-101 | Core Banking Cloud Migration | CIO Office | Stage 2 cutover completed without downtime | None | Approve Phase 3 production launch date | 2026-11-05 | On Track
PRJ-102 | Next-Gen Mobile App v4.0 | VP Digital | UAT completed with 98% pass rate | Third-party KYC API SLA risk | Approve soft-launch employee beta test | 2026-10-28 | On Track
PRJ-105 | Enterprise ERP SAP Upgrade | CFO Office | Initial architectural blueprint finalized | Budget variance currently exceeds 8% | Review CR-103 scope expansion | 2026-11-02 | At Risk

## Benefits & ROI Realization
📈 BUSINESS VALUE, BENEFITS REALIZATION & ROI TRACKER
Total Projected Benefit ($):
PROJECT ID | PROJECT NAME | BENEFIT CATEGORY | PROJECTED ANNUAL VALUE ($) | REALIZED VALUE ($) | PAYBACK PERIOD (MONTHS) | EST. ROI % | BENEFIT STATUS
PRJ-101 | Core Banking Cloud Migration | Datacenter License Reduction | 850000 | 420000 | 18 | 245% | Realizing
PRJ-102 | Next-Gen Mobile App v4.0 | Customer Conversion Uplift | 1200000 | 150000 | 12 | 310% | On Track
PRJ-103 | Data Lakehouse Real-time Streaming | Manual Reporting Time Saved | 450000 | 220000 | 14 | 185% | Realizing
PRJ-104 | Zero Trust Identity Architecture | Security Breach Mitigation | 600000 | 300000 | 20 | 150% | Realizing

## Quality Gates & UAT
🧪 QUALITY GATES, USER ACCEPTANCE TESTING (UAT) & GO/NO-GO
GATE ID | PROJECT NAME | TESTING PHASE | TEST CASES TOTAL | PASSED CASES | FAILED CASES | PASS RATE % | BLOCKER DEFECTS | DECISION
QG-101 | Core Banking Cloud Migration | System Integration Test (SIT) | 1250 | 1240 | 10 |  | 0 | Go
QG-102 | Next-Gen Mobile App v4.0 | User Acceptance Test (UAT) | 680 | 672 | 8 |  | 0 | Go
QG-103 | Data Lakehouse Real-time Streaming | End-to-End Load Testing | 450 | 435 | 15 |  | 1 | At Risk

## Strategic PMO Scorecard
🏆 STRATEGIC PMO DELIVERY MATURITY & PERFORMANCE SCORECARD
PERSPECTIVE | STRATEGIC OBJECTIVE | TARGET KPI | ACTUAL ACHIEVED | WEIGHT | SCORE (0-100) | WEIGHTED SCORE | RAG STATUS
Portfolio Schedule | Achieve > 85% milestones delivered on baseline schedule | >= 85.0% | 88.2% | 25% | 92 |  | Optimal
Financial EVM | Deliver portfolio with Cost Performance Index (CPI) >= 1.0 | >= 1.00 |  | 25% | 95 |  | Optimal
Agile Predictability | Squad sprint story point predictability >= 85% | >= 85.0% |  | 20% | 96 |  | Optimal
Risk Governance | Remediate 100% of critical RAID blockers within 14 days | 100.0% | 94.0% | 15% | 90 |  | Optimal
Business Value & ROI | Achieve target ROI within 18 months of go-live | >= 100.0% | 142.5% | 15% | 94 |  | Optimal
OVERALL IT PMO MATURITY INDEX | [6 empty] | Elite (Grade A)