## Instructions
SOFTWARE ENGINEERING, DEVOPS & QA ENTERPRISE DASHBOARD
Engineering Operations, DORA Metrics, Agile Velocity & Quality Architecture Guide
FRAMEWORK OVERVIEW & ARCHITECTURE
Topic / Sheet | Description / Guidance
Core Engineering Scope | Covers the complete Software Development Life Cycle (SDLC): Agile Sprints, DORA Performance, Defect Tracking, CI/CD Health, SonarQube Code Quality, Team Allocation, and Release Trains.
DORA Metrics Benchmark | Follows Google Cloud DevOps Research and Assessment (DORA) standards: Deployment Frequency, Lead Time for Changes, Change Failure Rate, and Time to Restore Service (MTTR).
Automated Rollups | All executive cards, burndown indicators, pass rates, and performance tiers are dynamically calculated via Excel formulas without manual re-keying.
MODULE DIRECTORY (14 SHEETS)
Topic / Sheet | Description / Guidance
1. Executive SDLC Dashboard | Unified CTO / VP Engineering cockpit featuring DORA KPIs, sprint velocity trend chart, defect severity breakdown, and team health matrix.
2. DORA Metrics Tracker | Weekly and monthly tracking of the 4 DORA metrics with automated classification into Elite, High, Medium, or Low performers.
3. Sprint & Velocity Log | Agile sprint tracking: Story points committed vs completed, velocity predictability %, and spillover analysis.
4. Epics & Features Roadmap | High-level feature tracking with tech leads, product owners, milestone progress %, and delivery RAG status.
5. Bug & Defect Register | Production & staging defect tracker with automated resolution hours, SLA breach detection, and root cause categorization.
6. CI/CD Pipeline Health | Pipeline success rates across GitHub Actions & GitLab CI, build runtimes, and flaky test frequency.
7. Code Quality & SonarQube | Static code analysis: Test coverage %, technical debt in days, code smells, and automated Quality Gate pass/fail flags.
8. Developer Capacity & Pods | Cross-functional pod capacity planning (Core Platform, Checkout, Logistics) and focus ratio across new features vs tech debt.
9. Release Management | Release train management, Go/No-Go checklists, hotfix tracking, and deployment outcome governance.
10. API & Microservices | Microservice catalog tracking service ownership, P99 response latency, error rates, and uptime SLAs.
11. QA & Automated Testing | End-to-end (E2E), integration, and unit test automation coverage %, execution runtimes, and pass rates.
12. Tech Debt & Architecture | Architecture Decision Records (ADRs) and technical debt backlog prioritization with story point effort estimations.
13. Engineering Balanced Scorecard | Executive scorecard consolidating 12 engineering KPIs across Speed, Stability, Quality, and Developer Happiness.
DORA PERFORMANCE TIERS REFERENCE
Topic / Sheet | Description / Guidance
Elite Performer | Deploy Multiple times/day ¦ Lead Time < 1 hour ¦ Change Failure < 5% ¦ MTTR < 1 hour
High Performer | Deploy Once per day to once/week ¦ Lead Time 1 day - 1 week ¦ Change Failure 5-10% ¦ MTTR < 1 day
Medium Performer | Deploy Once per week to once/month ¦ Lead Time 1 week - 1 month ¦ Change Failure 10-15% ¦ MTTR < 1 day
Low Performer | Deploy Less than once/month ¦ Lead Time > 1 month ¦ Change Failure > 15% ¦ MTTR > 1 week

## Executive SDLC Dashboard
SOFTWARE ENGINEERING & DEVOPS EXECUTIVE COCKPIT
DORA Metrics, Sprint Velocity, Defect Density, CI/CD Reliability & Code Health
DEPLOYMENT FREQUENCY |  |  | CHANGE FAILURE RATE |  |  | LEAD TIME FOR CHANGES |  |  | TIME TO RESTORE SERVICE
Formula Driven Metric |  |  | Formula Driven Metric |  |  | Formula Driven Metric |  |  | Formula Driven Metric
AVG SPRINT VELOCITY |  |  | OPEN CRITICAL / HIGH BUGS |  |  | OVERALL CODE COVERAGE |  |  | CI/CD BUILD SUCCESS RATE
Formula Driven Metric |  |  | Formula Driven Metric |  |  | Formula Driven Metric |  |  | Formula Driven Metric
SPRINT VELOCITY & STORY POINTS TREND | [6 empty] | DEFECT DISTRIBUTION BY SEVERITY
Metric | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Severity | Count
Committed | 120 | 135 | 125 | 140 | 150 | 145 | Critical (P1) | 3
Completed | 112 | 128 | 122 | 138 | 142 | 140 | Major (P2) | 8
[7 empty] | Minor (P3) | 19
[7 empty] | Trivial (P4) | 12
ENGINEERING HEALTH & DELIVERY RISK SCORECARD
Engineering Domain | Target Standard | Measurement Focus | Benchmark | Actual Score | Operational Status | Health Grade
Deployment Cadence | >= 10 Deploys / Week | DORA Deployment Frequency | DORA High Performer |  | High Throughput | ELITE
Delivery Lead Time | <= 24 Hours | Code Commit to Production Release | DORA High Performer |  | Fast Cycle Time | HIGH
Production Reliability | <= 5.0% | Change Failure Rate (Hotfix/Rollback) | DORA Elite: < 5% |  | Low Failure Rate | ELITE
Incident Recovery (MTTR) | <= 2.0 Hours | Time to Restore Production Service | DORA High: < 1 Day |  | Resilient Architecture | HIGH
Sprint Predictability | >= 90.0% | Story Points Delivered / Committed | Agile Standard: 85-90% |  | High Predictability | GREEN
Code Quality & Tests | >= 80.0% | SonarQube Unit Test Line Coverage | Clean Code Std: 80% |  | Robust Coverage | GREEN
CI/CD Automation | >= 95.0% | Automated Build & Test Pass Rate | DevOps Std: 95% | 96.4% | Stable Pipelines | GREEN
| Monthly DORA Deployment Frequency & Lead Time Reduction (%) |  |  |  |  | Software Engineering & DevOps (DORA) Index
| Month | Target DORA Index % | Actual DORA Maturity % | Change Failure Rate Def % |  | Operational Capability Pillar | Benchmark | Current Attainment
| May | 85 | 86.8 | 94 |  | Continuous Deployment CD | 4.2 | 4.8
| Jun | 88 | 89.5 | 95.5 |  | Trunk-Based Development | 4 | 4.6
| Jul | 90 | 91.8 | 96.8 |  | Automated Test Suite Speed | 4 | 4.5
| Aug | 90 | 91.2 | 96.4 |  | Observability Distributed Trace | 4.2 | 4.7
| Sep | 93 | 94.5 | 98 |  | Developer Ergonomics DevEx | 3.8 | 4.4
| Oct | 96 | 97.2 | 99.1 |  | Security SAST Shift-Left | 4.2 | 4.8
| Engineering Story Points Delivered by Work Stream |  |  |  |  | Pull Request Cycle Time (Hours) vs Code Review Depth (Comments)
| Month | Feature Innovations | Architecture & Refactor | Bug Fixes | Tech Debt Burn | Team Squad | Cycle Time (Hrs) | Review Comments | PRs Shipped
| May | 420 | 140 | 95 | 65 | Squad-Core-Engine | 14 | 8.5 | 65
| Jun | 460 | 155 | 88 | 72 | Squad-Checkout | 18 | 11.2 | 48
| Jul | 510 | 175 | 80 | 85 | Squad-Mobile-App | 9.5 | 5.8 | 92
| Aug | 495 | 168 | 82 | 80 | Squad-Data-Pipeline | 24 | 14 | 34
| Sep | 560 | 190 | 75 | 95 | Squad-Platform-SRE | 12 | 7.2 | 58
| Oct | 620 | 210 | 68 | 110 | Squad-Frontend-Design | 8 | 4.5 | 110

## DORA Metrics
DORA METRICS & DEVOPS CAPABILITY EVALUATION
Google Cloud DORA Standard: Speed vs Stability Balance Matrix
DORA Pillar | Metric Name | Current Measurement | Actual Performance | Target Threshold | DORA Performance Tier | Industry Benchmark
Throughput (Speed) | Deployment Frequency | Number of production releases per week | 14.5 | >= 10 / Wk | Elite | Multiple deploys per day
Throughput (Speed) | Lead Time for Changes | Average hours from commit to prod deployment | 18.2 | <= 24.0 Hrs | High | Between 1 day and 1 week
Stability (Quality) | Change Failure Rate | % of production deploys causing incident/rollback | 3.8% | <= 5.0% | Elite | Less than 5%
Stability (Quality) | Time to Restore Service (MTTR) | Mean time in hours to remediate production outage | 1.4 | <= 2.0 Hrs | High | Less than 1 day
WEEKLY DORA AUDIT LOG (LAST 8 WEEKS)
Audit Week | Total Deploys | Lead Time (Hrs) | Failed Deploys | Change Failure Rate % | Total Downtime (Mins) | MTTR (Hrs) | Weekly DORA Tier
Week 10 (Current) | 16 | 17.5 | 0 |  | 0 | 1.2
Week 09 | 15 | 18 | 1 |  | 45 | 1.5
Week 08 | 14 | 19.2 | 0 |  | 0 | 1.4
Week 07 | 13 | 21 | 1 |  | 60 | 2
Week 06 | 16 | 16.5 | 0 |  | 0 | 1.1
Week 05 | 12 | 22 | 1 |  | 90 | 2.5
Week 04 | 15 | 17.8 | 0 |  | 0 | 1.3
Week 03 | 14 | 18.5 | 1 |  | 35 | 1.4

## Sprint & Velocity Log
AGILE SPRINT PLANNING & VELOCITY PREDICTABILITY LOG
Committed vs Delivered Story Points, Velocity Variance, & Team Performance Trends
AVERAGE VELOCITY: |  |  | OVERALL PREDICTABILITY: |  |  | TOTAL SPILLOVER PTS:
Sprint ID | Pod / Squad Name | Start Date | Committed Pts | Completed Pts | Spillover Pts | Velocity Predictability % | Target End Date | Retro Action Items | Team Happiness (1-5) | Scrum Master | Sprint Status
SPR-2026-S25 | Checkout & Payments Pod | 2026-03-01 | 145 | 140 |  |  | 2026-03-14 | Simplify 3DS verification mocks | 4.5 | Yusuf Hakim | Active
SPR-2026-S24 | Checkout & Payments Pod | 2026-02-15 | 150 | 142 |  |  | 2026-02-28 | Add load tests for payment webhook | 4.2 | Yusuf Hakim | Completed
SPR-2026-S23 | Checkout & Payments Pod | 2026-02-01 | 140 | 138 |  |  | 2026-02-14 | Split large epic into smaller PRs | 4.4 | Yusuf Hakim | Completed
SPR-2026-S22 | Core Platform & Infra Pod | 2026-03-01 | 110 | 104 |  |  | 2026-03-14 | Automate EKS spot instance drains | 4.3 | Nadia Safitri | Active
SPR-2026-S21 | Core Platform & Infra Pod | 2026-02-15 | 120 | 115 |  |  | 2026-02-28 | Improve Terraform state lock timing | 4.1 | Nadia Safitri | Completed
SPR-2026-S20 | Growth & Mobile Pod | 2026-03-01 | 95 | 92 |  |  | 2026-03-14 | Optimize iOS build compilation flags | 4.6 | Rendy Pratama | Active
SPR-2026-S19 | Growth & Mobile Pod | 2026-02-15 | 100 | 94 |  |  | 2026-02-28 | Resolve Android Jetpack Compose re-render | 4 | Rendy Pratama | Completed

## Epics Roadmap
PRODUCT & ENGINEERING ROADMAP (EPICS & INITIATIVES)
Strategic Feature Deliverables, Story Point Weighting, Progress & Delivery Health
TOTAL ACTIVE EPICS: |  |  | AVERAGE COMPLETION: |  |  | ON-TRACK INITIATIVES:
Epic Key | Feature Initiative Name | Assigned Pod | Product Owner | Tech Lead | Total Story Pts | Completed Pts | Progress % | RAG Status | Target Quarter | Dependency / Risk | Release Milestone
EPC-001 | Instant Bank Transfer (BI-FAST Integration) | Checkout & Payments | Diana Putri | Budi Hermawan | 85 | 75 |  | On Track | Q1 2026 | Bank API rate limits | v2.4.0
EPC-002 | Single-Sign-On (SSO) SAML 2.0 Enterprise | Core Platform | Faris Gunawan | Alex Kurniawan | 60 | 48 |  | On Track | Q1 2026 | Okta SCIM synchronization | v2.4.0
EPC-003 | AI-Powered Product Recommendations Engine | Growth & Personalization | Sarah Azhari | Kevin Sanjaya | 120 | 60 |  | Needs Attention | Q2 2026 | Feature store model latency | v2.5.0
EPC-004 | Warehouse Real-Time Barcode Scanner App | Logistics & Ops | Hendra Setiawan | Rian Pratama | 95 | 90 |  | On Track | Q1 2026 | Zebra hardware SDK driver | v2.4.1
EPC-005 | Checkout Micro-Frontend (Next.js v15) | Web Experience | Lisa Amelia | Budi Hermawan | 110 | 35 |  | On Track | Q2 2026 | Legacy bundle tree-shaking | v2.5.0
EPC-006 | Kafka Event Streaming Decoupling | Core Platform | Faris Gunawan | Alex Kurniawan | 75 | 70 |  | On Track | Q1 2026 | Consumer rebalance lag | v2.4.0

## Bug & Defect Register
BUG & DEFECT QUALITY REGISTER (STAGING & PRODUCTION)
Defect Density, Escaped Bugs, Severity Triage, SLA Breach & Root Cause Analysis
TOTAL LOGGED BUGS: |  |  | ESCAPED TO PRODUCTION: |  |  | RESOLVED BUGS:
Bug ID | Bug Summary Description | Severity | Environment | Impacted Component | Assigned Developer | Defect Status | Reported Date | Resolved Date | Resolution (Hrs) | Target SLA (Hrs) | SLA Compliance | Root Cause Category
BUG-101 | Payment gateway 500 error when currency string contains symbols | Critical | Production | Checkout Service | Budi Hermawan | Resolved | 2026-03-01 10:00 | 2026-03-01 12:30 |  |  |  | Unhandled Regex Exception
BUG-102 | iOS App crashing on launch on iOS 18.2 beta builds | Major | Production | iOS Native App | Rendy Pratama | Resolved | 2026-03-02 09:15 | 2026-03-02 16:00 |  |  |  | Deprecated Framework API
BUG-103 | Inventory count negative when 2 users checkout simultaneously | Critical | Production | Inventory DB | Alex Kurniawan | Resolved | 2026-03-03 14:00 | 2026-03-03 17:15 |  |  |  | Missing Database Row Lock
BUG-104 | Notification badge not clearing after reading promotional inbox | Trivial | Staging | Frontend Web | Lisa Amelia | Closed | 2026-03-04 11:30 | 2026-03-05 14:00 |  |  |  | Frontend State Cache Sync
BUG-105 | User profile avatar upload failing for PNG format > 5MB | Minor | Production | User Service | Kevin Sanjaya | Resolved | 2026-03-05 08:45 | 2026-03-06 10:00 |  |  |  | Nginx Upload Buffer Limit
BUG-106 | Order history filter date range offset by UTC timezone | Minor | Production | Order Service | Budi Hermawan | Open | 2026-03-08 10:00 |  |  |  |  | Timezone Parsing
BUG-107 | Search autocomplete dropdown laggy on mobile safari | Minor | Staging | Search API | Kevin Sanjaya | In Progress | 2026-03-09 13:00 |  |  |  |  | Missing Debounce Handler

## CI-CD Pipeline Health
CONTINUOUS INTEGRATION & DELIVERY (CI/CD) PIPELINE MONITORING
Build Runtimes, Pipeline Pass Rates, Flaky Tests, & Automated Deployment Success
OVERALL PASS RATE: |  |  | AVG BUILD DURATION: |  |  | TOTAL FLAKY TESTS:
Repository / Service | Default Branch | CI Tool | Total Builds (Mo) | Passed Builds | Failed Builds | Pass Rate % | Avg Duration (Min) | Flaky Tests Flagged | Deployment Target | Pipeline Maintainer
core-checkout-api | main | GitHub Actions | 240 | 234 |  |  | 4.2 | 2 | AWS EKS Production | Alex Kurniawan
frontend-web-portal | main | GitHub Actions | 310 | 298 |  |  | 5.8 | 5 | Vercel / Cloudflare | Lisa Amelia
mobile-customer-app | develop | GitLab CI Runner | 180 | 168 |  |  | 12.5 | 8 | Firebase App Distribution | Rendy Pratama
inventory-service | main | GitHub Actions | 145 | 142 |  |  | 3.8 | 1 | AWS EKS Production | Alex Kurniawan
auth-identity-service | main | GitHub Actions | 120 | 118 |  |  | 3.2 | 0 | AWS ECS Fargate | Kevin Sanjaya
data-warehouse-dbt | main | GitHub Actions | 95 | 93 |  |  | 8.5 | 3 | BigQuery Production | Bambang Wijaya
notifications-worker | main | GitHub Actions | 80 | 79 |  |  | 2.4 | 0 | AWS Lambda Serverless | Budi Hermawan

## Code Quality & SonarQube
STATIC CODE ANALYSIS & TECHNICAL DEBT (SONARQUBE)
Code Coverage, Maintainability Rating, Code Smells, & Quality Gate Governance
AVERAGE CODE COVERAGE: |  |  | TOTAL TECHNICAL DEBT: |  |  | QUALITY GATES PASSED:
Repository / Microservice | Primary Language | Lines of Code (LOC) | Test Coverage % | Maintainability Rating | Code Smells Count | Duplicated Lines % | Tech Debt (Days) | Quality Gate Status | Open Vulnerabilities | Security Hotspots | Lead Architect
core-checkout-api | Golang 1.22 | 48500 | 88.5% | A - Clean | 14 | 1.8% | 4.5 | Passed | 0 | 2 | Budi Hermawan
frontend-web-portal | TypeScript / Next.js | 62000 | 79.2% | B - Moderate | 42 | 3.5% | 12 | Passed | 0 | 5 | Lisa Amelia
mobile-customer-app | Kotlin & Swift | 84000 | 76% | B - Moderate | 58 | 4.2% | 16.5 | Passed | 0 | 4 | Rendy Pratama
inventory-service | Golang 1.22 | 32000 | 91% | A - Clean | 8 | 1.2% | 2 | Passed | 0 | 1 | Alex Kurniawan
auth-identity-service | Python / FastAPI | 28000 | 94% | A - Clean | 6 | 0.9% | 1.5 | Passed | 0 | 0 | Kevin Sanjaya
data-warehouse-dbt | SQL & Python | 19500 | 82% | A - Clean | 12 | 2.1% | 3 | Passed | 0 | 0 | Bambang Wijaya
notifications-worker | Node.js 20 | 15200 | 85.5% | A - Clean | 9 | 1.5% | 2.5 | Passed | 0 | 1 | Budi Hermawan

## Developer Capacity & Pods
ENGINEERING POD CAPACITY PLANNING & RESOURCE ALLOCATION
Team Capacity, Hours Allocation, Focus Ratio (Features vs Tech Debt vs Bugs)
TOTAL DEV WORKFORCE: |  |  | TOTAL SPRINT HOURS: |  |  | AVG NEW FEATURE FOCUS:
Engineer Name | Squad / Pod Name | Engineering Role | Seniority | Avail Sprint Hours | New Features % | Bug Fixes % | Tech Debt % | On-Call Support % | Estimated Velocity (Pts) | Pod Lead
Budi Hermawan | Checkout & Payments | Backend Engineer | Senior / Lead | 75 | 65% | 15% | 10% | 10% | 24 | Budi Hermawan
Taufik Ramli | Checkout & Payments | Backend Engineer | Mid-Level | 80 | 70% | 15% | 10% | 5% | 20 | Budi Hermawan
Agus Kurniawan | Checkout & Payments | QA Automation | Senior | 80 | 60% | 25% | 10% | 5% | 18 | Budi Hermawan
Lisa Amelia | Web Experience | Frontend Engineer | Senior | 75 | 70% | 15% | 10% | 5% | 22 | Lisa Amelia
Doni Setiawan | Web Experience | Frontend Engineer | Mid-Level | 80 | 75% | 15% | 10% | 0% | 18 | Lisa Amelia
Rendy Pratama | Growth & Mobile | Mobile Engineer (Android) | Senior | 75 | 65% | 20% | 10% | 5% | 20 | Rendy Pratama
Clara Shinta | Growth & Mobile | Mobile Engineer (iOS) | Senior | 75 | 65% | 20% | 10% | 5% | 20 | Rendy Pratama
Alex Kurniawan | Core Platform & Infra | DevOps / SRE | Staff Engineer | 70 | 40% | 20% | 25% | 15% | 22 | Alex Kurniawan
Kevin Sanjaya | Core Platform & Infra | Backend Engineer | Senior | 75 | 50% | 20% | 20% | 10% | 20 | Alex Kurniawan

## Release Management
ENTERPRISE RELEASE TRAIN & DEPLOYMENT GOVERNANCE
Release Versions, Go/No-Go Gateways, Hotfix Velocity, & Deployment Retrospectives
TOTAL 2026 RELEASES: |  |  | HOTFIX-FREE RATE: |  |  | SUCCESSFUL RELEASES:
Release Version | Release Date | Target Platforms | Scope / Deliverables Summary | QA Sign-off | Security Scan Passed | Rollback Plan Ready | Hotfixes Required | Deployment Outcome | Rollback Time (Mins) | Release Lead | CAB Ticket Reference
v2.4.0 | 2026-03-05 | Backend EKS & Web | BI-FAST payment gateway and user SAML SSO | Approved | Passed | Verified | 0 | Successful | 0 | Alex Kurniawan | CAB-2026-042
v2.3.2 | 2026-02-20 | iOS & Android | Hotfix for iOS 18 notification permission modal | Approved | Passed | Verified | 1 | Successful | 0 | Rendy Pratama | CAB-2026-038
v2.3.1 | 2026-02-12 | Backend EKS | Database connection pool scale-up & query index | Approved | Passed | Verified | 0 | Successful | 0 | Alex Kurniawan | CAB-2026-031
v2.3.0 | 2026-02-01 | Full Stack Suite | New warehouse logistics scanner & inventory lock | Approved | Passed | Verified | 0 | Successful | 0 | Budi Hermawan | CAB-2026-025
v2.2.0 | 2026-01-15 | Web & Mobile | Lunar New Year promotion banner & dynamic coupons | Approved | Passed | Verified | 0 | Successful | 0 | Lisa Amelia | CAB-2026-011

## API & Microservices
MICROSERVICES & API INVENTORY CATALOG
Service Tiering, Protocol, Latency SLAs (P99), Error Rate %, & Ownership Mapping
TOTAL SERVICES: |  |  | AVERAGE P99 LATENCY: |  |  | TIER-1 SERVICES COMPLIANT:
Microservice Name | Business Domain | Criticality Tier | Protocol | Hosting Environment | Owning Pod | Tech Lead | P99 Latency (ms) | Target Latency (ms) | Error Rate % | Target SLA % | Service Health
payment-gateway-service | Payments | Tier 1 | gRPC & REST | AWS EKS (c6i.xlarge) | Checkout & Payments | Budi Hermawan | 145 | 250 | 0.08% | 99.95% | Healthy
checkout-orchestrator | Checkout | Tier 1 | gRPC Internal | AWS EKS (c6i.xlarge) | Checkout & Payments | Budi Hermawan | 120 | 200 | 0.05% | 99.95% | Healthy
auth-identity-provider | Security | Tier 1 | REST & OAuth2 | AWS ECS Fargate | Core Platform | Kevin Sanjaya | 85 | 150 | 0.02% | 99.99% | Healthy
catalog-search-api | Search | Tier 2 | REST & Elasticsearch | AWS EKS (r6i.xlarge) | Search & Discovery | Kevin Sanjaya | 95 | 180 | 0.12% | 99.9% | Healthy
inventory-ledger-service | Logistics | Tier 1 | gRPC & Kafka | AWS EKS (m6i.xlarge) | Logistics & Ops | Alex Kurniawan | 110 | 200 | 0.04% | 99.95% | Healthy
notification-dispatcher | Communication | Tier 3 | Kafka Consumer | AWS Lambda Serverless | Platform Ops | Lisa Amelia | 320 | 500 | 0.2% | 99.5% | Healthy
analytics-event-collector | Data | Tier 2 | REST & Kinesis | AWS EKS (c6i.large) | Data Platform | Bambang Wijaya | 65 | 100 | 0.01% | 99.9% | Healthy

## QA & Automated Testing
QUALITY ASSURANCE & AUTOMATED TEST SUITE REPORT
End-to-End, Integration, API, & Unit Test Coverage, Pass Rates & Execution Durations
TOTAL TEST CASES: |  |  | AUTOMATION RATIO: |  |  | OVERALL TEST PASS RATE:
Test Suite Name | Test Framework / Tool | Total Test Cases | Automated Cases | Automation % | Passed Tests | Failed Tests | Pass Rate % | Execution Time (Min) | Execution Cadence | QA Suite Owner
Checkout E2E Critical Path | Playwright (TypeScript) | 240 | 235 |  | 232 |  |  | 14.5 | Per PR & Nightly | Agus Kurniawan
Mobile App Regression Suite | Appium & Maestro | 380 | 310 |  | 302 |  |  | 35 | Nightly | Siti Nurhaliza
Core Microservices API Suite | Postman / Newman & Go | 520 | 520 |  | 516 |  |  | 8.2 | Per PR Commit | Agus Kurniawan
Frontend Visual Regression | Percy & Storybook | 185 | 185 |  | 183 |  |  | 6 | Per PR Commit | Lisa Amelia
Identity & Auth Security Tests | OWASP ZAP & Custom | 95 | 95 |  | 95 |  |  | 12 | Weekly Scheduled | Kevin Sanjaya
Data Pipeline Schema Tests | Great Expectations | 150 | 150 |  | 148 |  |  | 5.5 | Daily Scheduled | Bambang Wijaya

## Tech Debt & Architecture
TECHNICAL DEBT REGISTER & ARCHITECTURE DECISION RECORDS (ADR)
Architectural Debt Prioritization, Remediation Effort Estimations, & Refactoring Sprints
TOTAL LOGGED DEBT: |  |  | TOTAL REMEDIATION EFFORT: |  |  | RESOLVED DEBT ITEMS:
Debt ID | Architectural Concern / Refactoring Item | Impacted Microservice | Risk Category | Impact on System | Priority | Effort (Story Pts) | Assigned Squad | Target Sprint | Resolution Status | ADR Reference | Tech Sponsor
TDB-001 | Migrate legacy MySQL monolithic table to Aurora PostgreSQL partitioned table | order-database | Scalability | High query lock during peak flash sales | Critical | 34 | Checkout & Payments | Sprint 26 | In Progress | ADR-2026-004 | Alex Kurniawan
TDB-002 | Replace unmaintained third-party PDF invoice generator library | invoice-worker | Security & Supply Chain | Potential memory leak on bulk billing | High | 13 | Core Platform | Sprint 26 | Scheduled | ADR-2026-008 | Kevin Sanjaya
TDB-003 | Decouple synchronous HTTP calls between checkout and inventory to Kafka events | checkout-api | Reliability | Cascading timeouts when inventory latency spikes | Critical | 21 | Checkout & Payments | Sprint 25 | In Progress | ADR-2026-002 | Budi Hermawan
TDB-004 | Upgrade React 17 legacy components to React 19 server components | frontend-web-portal | Maintainability | Sub-optimal initial bundle size on mobile web | Medium | 26 | Web Experience | Sprint 27 | Backlog | ADR-2026-011 | Lisa Amelia
TDB-005 | Convert manual bash deployment scripts to standard Helm charts | core-infrastructure | DevOps & Governance | Risk of deployment divergence across clusters | High | 15 | Core Platform | Sprint 24 | Resolved | ADR-2026-001 | Alex Kurniawan

## Engineering Scorecard
STRATEGIC ENGINEERING BALANCED SCORECARD & KPIS
Performance Metrics Across Velocity, Reliability, Code Health & Team Capacity
Engineering Dimension | Strategic KPI Indicator | Measurement Formula / Source | Target Standard | Actual Score | Variance | Health Status | Industry Benchmark | Review Cadence | Accountable Lead
Deployment Speed | Deployment Frequency (DORA) |  | >= 10 / Wk |  | Formula | Compliant | DORA Elite: Multiple/Day | Weekly | VP of Engineering
Deployment Speed | Lead Time for Changes (DORA) |  | <= 24.0 Hrs |  | Formula | Compliant | DORA High: < 1 Week | Weekly | DevOps Lead
System Stability | Change Failure Rate (DORA) |  | <= 5.0% |  | Formula | Compliant | DORA Elite: < 5% | Monthly | Lead Architect
System Stability | Mean Time to Restore (MTTR) |  | <= 2.0 Hrs |  | Formula | Compliant | DORA High: < 1 Day | Monthly | SRE / Ops Lead
Agile Predictability | Sprint Velocity Predictability |  | >= 90.0% |  | Formula | Compliant | Agile Target: 85-90% | Sprint End | Scrum Master
Software Quality | Production Defect Density | Escaped bugs per major release | <= 2 / Release | 0.8 / Release | -1.2 | Compliant | High Quality: < 2 | Bi-Weekly | Head of QA
Software Quality | Unit Test Line Coverage |  | >= 80.0% |  | Formula | Compliant | Industry Standard: 80% | Continuous | Tech Leads
CI/CD Automation | Pipeline Build Success Rate |  | >= 95.0% |  | Formula | Compliant | DORA High: 95% | Daily | DevOps Lead
Developer Health | Tech Debt Allocation Ratio | Hours spent on tech debt / Total hours | >= 15.0% | 17.5% | +2.5% | Compliant | Clean Code Std: 15-20% | Sprint End | VP of Engineering
Release Governance | Hotfix-Free Release Rate |  | >= 85.0% |  | Formula | Compliant | Standard: 80% | Monthly | Release Manager
QA Automation | Automated Test Coverage Ratio |  | >= 80.0% |  | Formula | Compliant | Automation Std: 80% | Bi-Weekly | Head of QA